## Dashboard
Dashboard
All numbers are formulas over the Tasks sheet.
| Start date (edit) | 2026-10-06 | ← set the day you start; every date moves with it
| Hours per day | 1 | Plan assumption from you: 1 h every day
Total tasks (= days)
Planned hours
Tasks done
% done
Actual hours logged
Actual h per done task
Reviews approved
Reviews waiting
Blocked tasks
Today is day #
Tasks expected done by today
Ahead (+) / behind (−)
Today's task
Next not-started task
Planned finish
Finish if 1 task/day from today
Pilot tasks (P0–P9)
Pilot tasks done
Pilot planned finish
Phases = milestones
| Phase | Tasks | Done | % done | Pilot | Start | Finish (planned) | Demo / done when
| P0 Learn & set up |  |  |  | Y |  |  | Tools installed, Spring Boot hello API runs in Docker with PostgreSQL, CI green
| P1 Platform & accounts (API) |  |  |  | Y |  |  | Register → verify email → login → refresh works via Postman/HTTP file; outbox delivers emails
| P2 App foundation + auth screens |  |  |  | Y |  |  | Customer + worker apps run on an Android phone; sign up, verify, log in, browse catalog
| P3 Addresses, worker profile, media |  |  |  | Y |  |  | Customer saves an address with map pin; worker completes profile, trades, rates, hours, area and uploads photo
| P4 Request & matching |  |  |  | Y |  |  | Customer posts a request → nearby workers get offers → say interested → customer picks one
| P5 Booking & job |  |  |  | Y |  |  | Worker goes on the way, checks in, start code, checks out; customer confirms; cancellations work
| P6 Cash, earnings, reviews |  |  |  | Y |  |  | Job paid in cash, ledger balanced, worker sees earnings + dues, both sides review
| P7 Notifications & account |  |  |  | Y |  |  | Push + email + inbox for key events; account, privacy and settings screens done
| P8 Verification & admin console |  |  |  | Y |  |  | Worker uploads ID; admin logs in with MFA, approves worker, looks up users, edits catalog
| P9 Pilot release (cash-only) |  |  |  | Y |  |  | Running on a VM with HTTPS + backups; Android builds with real workers in one Howrah zone
| P10 Online payments & payouts |  |  |  | N |  |  | Advance + online bill payment via provider sandbox, refunds, worker payouts
| P11 Quotes, disputes, realtime |  |  |  | N |  |  | Extra work quotes + material bills; disputes end to end; live updates without refresh
| P12 Full MVP release |  |  |  | N |  |  | All 22 LLDs live; production release on Play Store
By area
| Area | Tasks | Done | % done | Actual h
Admin web
App-Customer
App-Shared
App-Worker
Backend
DevOps
Learning
Ops
Review
Security
Testing
Total

## How to use
Karigar — Full MVP build tracker
One task = one hour = one day. You code it by hand; Claude reviews it.
Daily routine | 1) Open Dashboard → "Today's task". 2) Read the Doc ref first (5 min). 3) Code + test (45 min). 4) Commit on a branch, set Status = Done, Actual h, Review = Requested. 5) Ask Claude: "review task <Day#>" with the branch name.
Review flow | Requested → Claude reviews the diff against the LLD/screen → Changes needed (fix next day, before the new task) → Approved. Merge only after Approved.
Cells you edit | Yellow cells only: Dashboard start date; in Tasks the columns Status, Actual h, Review, PR / commit, Notes. Everything else is formulas or the plan.
Status values | Not started · In progress · Done · Blocked · Skipped
Review values | Not requested · Requested · Changes needed · Approved
Missed a day? | Do not skip ahead. Day 14 of every sprint is a catch-up day. The Dashboard shows how many tasks you are behind and the projected finish date.
Task too big? | Split it: add a row below with the same Day# and a note, or mark Status = In progress and continue tomorrow. Do not rewrite the plan; note it in Notes.
Pilot column | Y = needed for the cash-only pilot (phases P0–P9). N = full MVP after the pilot. The Dashboard shows both.
Example row (filled) | Day 20 · Status = Done · Actual h = 1.25 · Review = Approved · PR / commit = feat/outbox-writer#a1b2c3d · Notes = "Needed extra 15 min for Testcontainers"
Sources | Tasks are generated from docs/lld (22 LLDs, 216 endpoints, 86 tables) and docs/design/screens (244 frames). Estimates: 1 h per endpoint (code + test), 1 h per 2 tables per migration and per repository, 1 h per screen.
Honest note | Estimates assume you are learning while building. Real speed will differ: track Actual h and compare with the Est h on the Dashboard after the first sprint, then re-plan.

## Sprints
Sprints (2 weeks = 14 tasks; day 14 is review + catch-up)
Sprint | First day# | Start | End | Phases in sprint | Tasks | Done | % done | Reviews approved | Actual h | Retro notes
1 |  |  |  | P0 Learn & set up
2 |  |  |  | P0 Learn & set up · P1 Platform & accounts (API)
3 |  |  |  | P1 Platform & accounts (API)
4 |  |  |  | P1 Platform & accounts (API)
5 |  |  |  | P1 Platform & accounts (API)
6 |  |  |  | P1 Platform & accounts (API)
7 |  |  |  | P1 Platform & accounts (API)
8 |  |  |  | P1 Platform & accounts (API)
9 |  |  |  | P1 Platform & accounts (API) · P2 App foundation + auth screens
10 |  |  |  | P2 App foundation + auth screens
11 |  |  |  | P2 App foundation + auth screens
12 |  |  |  | P2 App foundation + auth screens · P3 Addresses, worker profile, media
13 |  |  |  | P3 Addresses, worker profile, media
14 |  |  |  | P3 Addresses, worker profile, media
15 |  |  |  | P3 Addresses, worker profile, media
16 |  |  |  | P3 Addresses, worker profile, media
17 |  |  |  | P3 Addresses, worker profile, media
18 |  |  |  | P3 Addresses, worker profile, media
19 |  |  |  | P3 Addresses, worker profile, media · P4 Request & matching
20 |  |  |  | P4 Request & matching
21 |  |  |  | P4 Request & matching
22 |  |  |  | P4 Request & matching
23 |  |  |  | P4 Request & matching
24 |  |  |  | P4 Request & matching
25 |  |  |  | P4 Request & matching
26 |  |  |  | P4 Request & matching
27 |  |  |  | P4 Request & matching · P5 Booking & job
28 |  |  |  | P5 Booking & job
29 |  |  |  | P5 Booking & job
30 |  |  |  | P5 Booking & job
31 |  |  |  | P5 Booking & job
32 |  |  |  | P5 Booking & job
33 |  |  |  | P5 Booking & job
34 |  |  |  | P5 Booking & job · P6 Cash, earnings, reviews
35 |  |  |  | P6 Cash, earnings, reviews
36 |  |  |  | P6 Cash, earnings, reviews
37 |  |  |  | P6 Cash, earnings, reviews
38 |  |  |  | P6 Cash, earnings, reviews
39 |  |  |  | P6 Cash, earnings, reviews
40 |  |  |  | P6 Cash, earnings, reviews · P7 Notifications & account
41 |  |  |  | P7 Notifications & account
42 |  |  |  | P7 Notifications & account
43 |  |  |  | P7 Notifications & account
44 |  |  |  | P7 Notifications & account · P8 Verification & admin console
45 |  |  |  | P8 Verification & admin console
46 |  |  |  | P8 Verification & admin console
47 |  |  |  | P8 Verification & admin console
48 |  |  |  | P8 Verification & admin console
49 |  |  |  | P8 Verification & admin console
50 |  |  |  | P8 Verification & admin console
51 |  |  |  | P8 Verification & admin console
52 |  |  |  | P8 Verification & admin console
53 |  |  |  | P8 Verification & admin console
54 |  |  |  | P8 Verification & admin console · P9 Pilot release (cash-only)
55 |  |  |  | P9 Pilot release (cash-only)
56 |  |  |  | P9 Pilot release (cash-only) · P10 Online payments & payouts
57 |  |  |  | P10 Online payments & payouts
58 |  |  |  | P10 Online payments & payouts
59 |  |  |  | P10 Online payments & payouts
60 |  |  |  | P10 Online payments & payouts
61 |  |  |  | P10 Online payments & payouts · P11 Quotes, disputes, realtime
62 |  |  |  | P11 Quotes, disputes, realtime
63 |  |  |  | P11 Quotes, disputes, realtime
64 |  |  |  | P11 Quotes, disputes, realtime
65 |  |  |  | P11 Quotes, disputes, realtime
66 |  |  |  | P11 Quotes, disputes, realtime
67 |  |  |  | P11 Quotes, disputes, realtime · P12 Full MVP release
68 |  |  |  | P12 Full MVP release

## Tasks
Day# | Date | Week | Sprint | Phase | Pilot | Area | Module | Task | Done when | Learn | Doc ref | Est h | Status | Actual h | Review | PR / commit | Notes
1 |  |  |  | P0 Learn & set up | Y | Learning | — | Install JDK 21, IntelliJ IDEA, Docker, git; clone repo | Notes in learning log; small sample committed | Tooling | operations/02 | 1 | Not started |  | Not requested
2 |  |  |  | P0 Learn & set up | Y | Learning | — | Read product overview + MVP scope | Notes in learning log; small sample committed | Product | product/04 | 1 | Not started |  | Not requested
3 |  |  |  | P0 Learn & set up | Y | Learning | — | Read architecture: modular monolith + package by module | Notes in learning log; small sample committed | Architecture | adr/0001, adr/0002 | 1 | Not started |  | Not requested
4 |  |  |  | P0 Learn & set up | Y | Learning | — | Java 21 refresher: records, sealed types, switch patterns, Optional | Notes in learning log; small sample committed | Java 21 |  | 1 | Not started |  | Not requested
5 |  |  |  | P0 Learn & set up | Y | Learning | — | Java streams + collections practice (5 small exercises) | Notes in learning log; small sample committed | Java 21 |  | 1 | Not started |  | Not requested
6 |  |  |  | P0 Learn & set up | Y | Learning | — | Create Spring Boot 3 project (start.spring.io), run GET /hello | Notes in learning log; small sample committed | Spring Boot |  | 1 | Not started |  | Not requested
7 |  |  |  | P0 Learn & set up | Y | Learning | — | Spring DI: beans, constructor injection, @Configuration, profiles | Notes in learning log; small sample committed | Spring Boot |  | 1 | Not started |  | Not requested
8 |  |  |  | P0 Learn & set up | Y | Learning | — | Spring Web: controllers, @Valid, ProblemDetail errors | Notes in learning log; small sample committed | Spring Web | api/01 | 1 | Not started |  | Not requested
9 |  |  |  | P0 Learn & set up | Y | Learning | — | docker-compose: PostgreSQL 17 + PostGIS + Redis | Notes in learning log; small sample committed | Docker | operations/02 | 1 | Not started |  | Not requested
10 |  |  |  | P0 Learn & set up | Y | Learning | — | SQL refresher in psql: joins, indexes, constraints, EXPLAIN | Notes in learning log; small sample committed | PostgreSQL | adr/0003 | 1 | Not started |  | Not requested
11 |  |  |  | P0 Learn & set up | Y | Learning | — | Flyway: first migration, naming V1_0__..., repeatable seeds | Notes in learning log; small sample committed | Flyway |  | 1 | Not started |  | Not requested
12 |  |  |  | P0 Learn & set up | Y | Learning | — | Spring Data JPA + Hibernate: entity, repository, transactions | Notes in learning log; small sample committed | JPA |  | 1 | Not started |  | Not requested
13 |  |  |  | P0 Learn & set up | Y | Learning | — | JUnit 5 + AssertJ: unit tests for a small class | Notes in learning log; small sample committed | Testing |  | 1 | Not started |  | Not requested
14 |  |  |  | P0 Learn & set up | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
15 |  |  |  | P0 Learn & set up | Y | Learning | — | Testcontainers: integration test on real PostgreSQL | Notes in learning log; small sample committed | Testing | adr/0015 | 1 | Not started |  | Not requested
16 |  |  |  | P0 Learn & set up | Y | Learning | — | Spring Security basics: filter chain, authentication | Notes in learning log; small sample committed | Security | security/01 | 1 | Not started |  | Not requested
17 |  |  |  | P0 Learn & set up | Y | Learning | — | JWT concepts: access vs refresh tokens, signing, expiry | Notes in learning log; small sample committed | Security | security/01 | 1 | Not started |  | Not requested
18 |  |  |  | P0 Learn & set up | Y | Learning | — | git workflow: branch per task, small commits, PR; how to ask Claude for review | Notes in learning log; small sample committed | Git |  | 1 | Not started |  | Not requested
19 |  |  |  | P0 Learn & set up | Y | Learning | — | GitHub Actions: build + test on every push | Notes in learning log; small sample committed | CI | operations/02 | 1 | Not started |  | Not requested
20 |  |  |  | P0 Learn & set up | Y | Learning | — | Read LLD template + LLD README build order | Notes in learning log; small sample committed | Process | lld/README.md | 1 | Not started |  | Not requested
21 |  |  |  | P0 Learn & set up | Y | Review | milestone | Milestone demo: Tools installed, Spring Boot hello API runs in Docker with PostgreSQL, CI green | Demo recorded; README updated | Demo | plan/ | 1 | Not started |  | Not requested
22 |  |  |  | P1 Platform & accounts (API) | Y | Learning | LLD-022 | Read LLD-022: Shared Platform — Outbox, Event Consumers, Idempotency, Reason Codes, Scheduled Jobs; list questions | Can explain the flow and tables | Domain | lld/lld-022-shared-platform.md | 1 | Not started |  | Not requested
23 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-022 | Flyway migration (1/3): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-022-shared-platform.md §3 | 1 | Not started |  | Not requested
24 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-022 | Flyway migration (2/3): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-022-shared-platform.md §3 | 1 | Not started |  | Not requested
25 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-022 | Flyway migration (3/3): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-022-shared-platform.md §3 | 1 | Not started |  | Not requested
26 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-022 | Entities + repositories (1/3) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-022-shared-platform.md §3 | 1 | Not started |  | Not requested
27 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-022 | Entities + repositories (2/3) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-022-shared-platform.md §3 | 1 | Not started |  | Not requested
28 |  |  |  | P1 Platform & accounts (API) | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
29 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-022 | Entities + repositories (3/3) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-022-shared-platform.md §3 | 1 | Not started |  | Not requested
30 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-022 | Module packages + ArchUnit rule: modules talk only through ports | Unit tests cover happy + failure paths | Domain logic | lld/lld-022-shared-platform.md §2/§5/§6 | 1 | Not started |  | Not requested
31 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-022 | Ids utility: UUIDv7 generator + unit test (ADR 0018) | Unit tests cover happy + failure paths | Domain logic | lld/lld-022-shared-platform.md §2/§5/§6 | 1 | Not started |  | Not requested
32 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-022 | Money type: integer paise, formatting, no floats (ADR 0006) | Unit tests cover happy + failure paths | Domain logic | lld/lld-022-shared-platform.md §2/§5/§6 | 1 | Not started |  | Not requested
33 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-022 | Error model: ProblemDetail + error codes (api/01) | Unit tests cover happy + failure paths | Domain logic | lld/lld-022-shared-platform.md §2/§5/§6 | 1 | Not started |  | Not requested
34 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-022 | OutboxWriter: write event in the same transaction | Unit tests cover happy + failure paths | Domain logic | lld/lld-022-shared-platform.md §2/§5/§6 | 1 | Not started |  | Not requested
35 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-022 | Outbox dispatcher: poll, deliver to in-process handlers, retry with backoff | Unit tests cover happy + failure paths | Domain logic | lld/lld-022-shared-platform.md §2/§5/§6 | 1 | Not started |  | Not requested
36 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-022 | processed_events: idempotent consumer wrapper + test | Unit tests cover happy + failure paths | Domain logic | lld/lld-022-shared-platform.md §2/§5/§6 | 1 | Not started |  | Not requested
37 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-022 | Idempotency-Key filter: store request hash + response, replay | Unit tests cover happy + failure paths | Domain logic | lld/lld-022-shared-platform.md §2/§5/§6 | 1 | Not started |  | Not requested
38 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-022 | Reason codes + translations lookup service | Unit tests cover happy + failure paths | Domain logic | lld/lld-022-shared-platform.md §2/§5/§6 | 1 | Not started |  | Not requested
39 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-022 | ShedLock for scheduled jobs + dead outbox events admin endpoint | Unit tests cover happy + failure paths | Domain logic | lld/lld-022-shared-platform.md §2/§5/§6 | 1 | Not started |  | Not requested
40 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-022 | API GET /api/v1/admin/ops/queues/OUTBOX_DEAD | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-022-shared-platform.md §4 | 1 | Not started |  | Not requested
41 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-022 | API POST /api/v1/admin/ops/outbox/{eventId}/retry | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-022-shared-platform.md §4 | 1 | Not started |  | Not requested
42 |  |  |  | P1 Platform & accounts (API) | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
43 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-022 | Events: publish/consume via outbox; check error handling §7 | Outbox rows written; consumer idempotent | Events | lld/lld-022-shared-platform.md §7 | 1 | Not started |  | Not requested
44 |  |  |  | P1 Platform & accounts (API) | Y | Review | LLD-022 | Module review with Claude: LLD-022 full diff + test plan §10 | All review comments fixed | Code review | lld/lld-022-shared-platform.md §10 | 1 | Not started |  | Not requested
45 |  |  |  | P1 Platform & accounts (API) | Y | Learning | LLD-001 | Read LLD-001: Email / Password Sign-up, Login and Email Verification; list questions | Can explain the flow and tables | Domain | lld/lld-001-identity-email-signup-login.md | 1 | Not started |  | Not requested
46 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-001 | Flyway migration (1/2): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-001-identity-email-signup-login.md §3 | 1 | Not started |  | Not requested
47 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-001 | Flyway migration (2/2): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-001-identity-email-signup-login.md §3 | 1 | Not started |  | Not requested
48 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-001 | Entities + repositories (1/2) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-001-identity-email-signup-login.md §3 | 1 | Not started |  | Not requested
49 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-001 | Entities + repositories (2/2) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-001-identity-email-signup-login.md §3 | 1 | Not started |  | Not requested
50 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-001 | Password hashing (Argon2/BCrypt) + password rules | Unit tests cover happy + failure paths | Domain logic | lld/lld-001-identity-email-signup-login.md §2/§5/§6 | 1 | Not started |  | Not requested
51 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-001 | JWT access token: sign, verify, claims, security filter chain | Unit tests cover happy + failure paths | Domain logic | lld/lld-001-identity-email-signup-login.md §2/§5/§6 | 1 | Not started |  | Not requested
52 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-001 | Email verification token: create, hash, expire | Unit tests cover happy + failure paths | Domain logic | lld/lld-001-identity-email-signup-login.md §2/§5/§6 | 1 | Not started |  | Not requested
53 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-001 | Send emails through the outbox to Brevo (sandbox key) | Unit tests cover happy + failure paths | Domain logic | lld/lld-001-identity-email-signup-login.md §2/§5/§6 | 1 | Not started |  | Not requested
54 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-001 | Login throttling / lockout rules | Unit tests cover happy + failure paths | Domain logic | lld/lld-001-identity-email-signup-login.md §2/§5/§6 | 1 | Not started |  | Not requested
55 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-001 | API POST /api/v1/auth/register | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-001-identity-email-signup-login.md §4 | 1 | Not started |  | Not requested
56 |  |  |  | P1 Platform & accounts (API) | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
57 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-001 | API POST /api/v1/auth/login | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-001-identity-email-signup-login.md §4 | 1 | Not started |  | Not requested
58 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-001 | API POST /api/v1/auth/email/verify | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-001-identity-email-signup-login.md §4 | 1 | Not started |  | Not requested
59 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-001 | API POST /api/v1/auth/email/verify/resend | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-001-identity-email-signup-login.md §4 | 1 | Not started |  | Not requested
60 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-001 | API POST /api/v1/auth/password/forgot | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-001-identity-email-signup-login.md §4 | 1 | Not started |  | Not requested
61 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-001 | API POST /api/v1/auth/password/reset | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-001-identity-email-signup-login.md §4 | 1 | Not started |  | Not requested
62 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-001 | Events: publish/consume via outbox; check error handling §7 | Outbox rows written; consumer idempotent | Events | lld/lld-001-identity-email-signup-login.md §7 | 1 | Not started |  | Not requested
63 |  |  |  | P1 Platform & accounts (API) | Y | Review | LLD-001 | Module review with Claude: LLD-001 full diff + test plan §10 | All review comments fixed | Code review | lld/lld-001-identity-email-signup-login.md §10 | 1 | Not started |  | Not requested
64 |  |  |  | P1 Platform & accounts (API) | Y | Learning | LLD-002 | Read LLD-002: Login Sessions, Token Issuing, Refresh Rotation and Logout; list questions | Can explain the flow and tables | Domain | lld/lld-002-identity-sessions-token-rotation.md | 1 | Not started |  | Not requested
65 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-002 | Flyway migration: tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-002-identity-sessions-token-rotation.md §3 | 1 | Not started |  | Not requested
66 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-002 | Entities + repositories + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-002-identity-sessions-token-rotation.md §3 | 1 | Not started |  | Not requested
67 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-002 | Refresh session table logic: issue + rotate | Unit tests cover happy + failure paths | Domain logic | lld/lld-002-identity-sessions-token-rotation.md §2/§5/§6 | 1 | Not started |  | Not requested
68 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-002 | Reuse detection: revoke the whole family | Unit tests cover happy + failure paths | Domain logic | lld/lld-002-identity-sessions-token-rotation.md §2/§5/§6 | 1 | Not started |  | Not requested
69 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-002 | Logout and logout-all | Unit tests cover happy + failure paths | Domain logic | lld/lld-002-identity-sessions-token-rotation.md §2/§5/§6 | 1 | Not started |  | Not requested
70 |  |  |  | P1 Platform & accounts (API) | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
71 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-002 | API POST /api/v1/auth/refresh | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-002-identity-sessions-token-rotation.md §4 | 1 | Not started |  | Not requested
72 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-002 | API POST /api/v1/auth/logout | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-002-identity-sessions-token-rotation.md §4 | 1 | Not started |  | Not requested
73 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-002 | API POST /api/v1/auth/logout-all | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-002-identity-sessions-token-rotation.md §4 | 1 | Not started |  | Not requested
74 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-002 | API GET /api/v1/me/sessions | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-002-identity-sessions-token-rotation.md §4 | 1 | Not started |  | Not requested
75 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-002 | API DELETE /api/v1/me/sessions/{familyId} | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-002-identity-sessions-token-rotation.md §4 | 1 | Not started |  | Not requested
76 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-002 | Events: publish/consume via outbox; check error handling §7 | Outbox rows written; consumer idempotent | Events | lld/lld-002-identity-sessions-token-rotation.md §7 | 1 | Not started |  | Not requested
77 |  |  |  | P1 Platform & accounts (API) | Y | Review | LLD-002 | Module review with Claude: LLD-002 full diff + test plan §10 | All review comments fixed | Code review | lld/lld-002-identity-sessions-token-rotation.md §10 | 1 | Not started |  | Not requested
78 |  |  |  | P1 Platform & accounts (API) | Y | Learning | LLD-003 | Read LLD-003: Catalog (Categories, Trades, Skills, Common Problems), Search and Language Resolution; list questions | Can explain the flow and tables | Domain | lld/lld-003-catalog-and-language.md | 1 | Not started |  | Not requested
79 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | Flyway migration (1/6): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-003-catalog-and-language.md §3 | 1 | Not started |  | Not requested
80 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | Flyway migration (2/6): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-003-catalog-and-language.md §3 | 1 | Not started |  | Not requested
81 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | Flyway migration (3/6): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-003-catalog-and-language.md §3 | 1 | Not started |  | Not requested
82 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | Flyway migration (4/6): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-003-catalog-and-language.md §3 | 1 | Not started |  | Not requested
83 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | Flyway migration (5/6): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-003-catalog-and-language.md §3 | 1 | Not started |  | Not requested
84 |  |  |  | P1 Platform & accounts (API) | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
85 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | Flyway migration (6/6): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-003-catalog-and-language.md §3 | 1 | Not started |  | Not requested
86 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | Entities + repositories (1/6) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-003-catalog-and-language.md §3 | 1 | Not started |  | Not requested
87 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | Entities + repositories (2/6) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-003-catalog-and-language.md §3 | 1 | Not started |  | Not requested
88 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | Entities + repositories (3/6) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-003-catalog-and-language.md §3 | 1 | Not started |  | Not requested
89 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | Entities + repositories (4/6) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-003-catalog-and-language.md §3 | 1 | Not started |  | Not requested
90 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | Entities + repositories (5/6) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-003-catalog-and-language.md §3 | 1 | Not started |  | Not requested
91 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | Entities + repositories (6/6) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-003-catalog-and-language.md §3 | 1 | Not started |  | Not requested
92 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | Seed data: categories, trades, problems (Flyway repeatable migration) | Unit tests cover happy + failure paths | Domain logic | lld/lld-003-catalog-and-language.md §2/§5/§6 | 1 | Not started |  | Not requested
93 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | en/bn/hi translations + language resolution (Accept-Language, user pref) | Unit tests cover happy + failure paths | Domain logic | lld/lld-003-catalog-and-language.md §2/§5/§6 | 1 | Not started |  | Not requested
94 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | Catalog search (PostgreSQL text search, ADR 0012) | Unit tests cover happy + failure paths | Domain logic | lld/lld-003-catalog-and-language.md §2/§5/§6 | 1 | Not started |  | Not requested
95 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | API GET /api/v1/catalog/locales | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-003-catalog-and-language.md §4 | 1 | Not started |  | Not requested
96 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | API GET /api/v1/catalog/categories | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-003-catalog-and-language.md §4 | 1 | Not started |  | Not requested
97 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | API GET /api/v1/catalog/professions/{id} | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-003-catalog-and-language.md §4 | 1 | Not started |  | Not requested
98 |  |  |  | P1 Platform & accounts (API) | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
99 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | API GET /api/v1/catalog/professions/{id}/skills | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-003-catalog-and-language.md §4 | 1 | Not started |  | Not requested
100 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | API GET /api/v1/catalog/professions/{id}/problems | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-003-catalog-and-language.md §4 | 1 | Not started |  | Not requested
101 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | API GET /api/v1/catalog/search | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-003-catalog-and-language.md §4 | 1 | Not started |  | Not requested
102 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | API POST /api/v1/admin/catalog/categories[/{id}] | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-003-catalog-and-language.md §4 | 1 | Not started |  | Not requested
103 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | API POST /api/v1/admin/catalog/professions[/{id}] | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-003-catalog-and-language.md §4 | 1 | Not started |  | Not requested
104 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | API POST /api/v1/admin/catalog/professions/{id}/activate | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-003-catalog-and-language.md §4 | 1 | Not started |  | Not requested
105 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | API POST /api/v1/admin/catalog/professions/{id}/skills[/{skillId}] | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-003-catalog-and-language.md §4 | 1 | Not started |  | Not requested
106 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | API POST /api/v1/admin/catalog/professions/{id}/problems[/{problemId}] | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-003-catalog-and-language.md §4 | 1 | Not started |  | Not requested
107 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | API PUT /api/v1/admin/catalog/{type}/{id}/translations/{locale} | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-003-catalog-and-language.md §4 | 1 | Not started |  | Not requested
108 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | API GET /api/v1/admin/catalog/search-misses | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-003-catalog-and-language.md §4 | 1 | Not started |  | Not requested
109 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | API GET /api/v1/admin/catalog/missing-translations | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-003-catalog-and-language.md §4 | 1 | Not started |  | Not requested
110 |  |  |  | P1 Platform & accounts (API) | Y | Backend | LLD-003 | Events: publish/consume via outbox; check error handling §7 | Outbox rows written; consumer idempotent | Events | lld/lld-003-catalog-and-language.md §7 | 1 | Not started |  | Not requested
111 |  |  |  | P1 Platform & accounts (API) | Y | Review | LLD-003 | Module review with Claude: LLD-003 full diff + test plan §10 | All review comments fixed | Code review | lld/lld-003-catalog-and-language.md §10 | 1 | Not started |  | Not requested
112 |  |  |  | P1 Platform & accounts (API) | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
113 |  |  |  | P1 Platform & accounts (API) | Y | Review | milestone | Milestone demo: Register → verify email → login → refresh works via Postman/HTTP file; outbox delivers emails | Demo recorded; README updated | Demo | plan/ | 1 | Not started |  | Not requested
114 |  |  |  | P2 App foundation + auth screens | Y | Learning | — | TypeScript basics: types, unions, generics, narrowing | Notes in learning log; small sample committed | TypeScript |  | 1 | Not started |  | Not requested
115 |  |  |  | P2 App foundation + auth screens | Y | Learning | — | TypeScript practice: type an API response + a reducer | Notes in learning log; small sample committed | TypeScript |  | 1 | Not started |  | Not requested
116 |  |  |  | P2 App foundation + auth screens | Y | Learning | — | React fundamentals: components, props, state, effects | Notes in learning log; small sample committed | React |  | 1 | Not started |  | Not requested
117 |  |  |  | P2 App foundation + auth screens | Y | Learning | — | React hooks: custom hooks, context, memo | Notes in learning log; small sample committed | React |  | 1 | Not started |  | Not requested
118 |  |  |  | P2 App foundation + auth screens | Y | Learning | — | React Native + Expo: create app, run on phone with Expo Go | Notes in learning log; small sample committed | React Native |  | 1 | Not started |  | Not requested
119 |  |  |  | P2 App foundation + auth screens | Y | Learning | — | Expo Router: stacks, tabs, protected routes | Notes in learning log; small sample committed | React Native |  | 1 | Not started |  | Not requested
120 |  |  |  | P2 App foundation + auth screens | Y | Learning | — | TanStack Query: queries, mutations, cache invalidation | Notes in learning log; small sample committed | Data fetching |  | 1 | Not started |  | Not requested
121 |  |  |  | P2 App foundation + auth screens | Y | Learning | — | Forms: react-hook-form + zod validation | Notes in learning log; small sample committed | Forms |  | 1 | Not started |  | Not requested
122 |  |  |  | P2 App foundation + auth screens | Y | DevOps | apps | Monorepo: apps/customer, apps/worker, packages/ui, packages/api (pnpm workspaces) | Both apps start; shared package imported | Monorepo | design/screens | 1 | Not started |  | Not requested
123 |  |  |  | P2 App foundation + auth screens | Y | App-Shared | ui | Design tokens from karigar.css → packages/ui theme (colours, gradients, radius, spacing) | Token file matches 00-foundations | Design tokens | design/screens/00-foundations.html | 1 | Not started |  | Not requested
124 |  |  |  | P2 App foundation + auth screens | Y | App-Shared | ui | Fonts: Anek Latin / Bangla / Devanagari with expo-font | All 3 scripts render | Fonts | design/screens/00-foundations.html | 1 | Not started |  | Not requested
125 |  |  |  | P2 App foundation + auth screens | Y | App-Shared | ui | Components: Button (primary/gradient/ghost), Input, Card | Match 01-components | Components | design/screens/01-components.html | 1 | Not started |  | Not requested
126 |  |  |  | P2 App foundation + auth screens | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
127 |  |  |  | P2 App foundation + auth screens | Y | App-Shared | ui | Components: Chip, Badge, ListItem, BottomSheet, Toast | Match 01-components | Components | design/screens/01-components.html | 1 | Not started |  | Not requested
128 |  |  |  | P2 App foundation + auth screens | Y | App-Shared | ui | Components: Loading, Empty, Error states + tool-pattern background | Match 01-components | Components | design/screens/01-components.html | 1 | Not started |  | Not requested
129 |  |  |  | P2 App foundation + auth screens | Y | App-Shared | api | API client: fetch wrapper, ProblemDetail errors, Idempotency-Key header | Errors shown as friendly messages | HTTP | api/01 | 1 | Not started |  | Not requested
130 |  |  |  | P2 App foundation + auth screens | Y | App-Shared | api | Auth: tokens in expo-secure-store, refresh on 401 with rotation | Token refresh works after expiry | Auth | lld-002 | 1 | Not started |  | Not requested
131 |  |  |  | P2 App foundation + auth screens | Y | App-Shared | i18n | i18next en/bn/hi + language switch saved to profile | Switch changes all strings | i18n | lld-003 | 1 | Not started |  | Not requested
132 |  |  |  | P2 App foundation + auth screens | Y | App-Customer | customer/01-auth.html | Screen C-01a — Splash | Matches frame; tokens only; loading/error states | UI | design/screens/customer/01-auth.html | 1 | Not started |  | Not requested
133 |  |  |  | P2 App foundation + auth screens | Y | App-Customer | customer/01-auth.html | Screen C-01b — Welcome | Matches frame; tokens only; loading/error states | UI | design/screens/customer/01-auth.html | 1 | Not started |  | Not requested
134 |  |  |  | P2 App foundation + auth screens | Y | App-Customer | customer/01-auth.html | Screen C-01c — Sign up | Matches frame; tokens only; loading/error states | UI | design/screens/customer/01-auth.html | 1 | Not started |  | Not requested
135 |  |  |  | P2 App foundation + auth screens | Y | App-Customer | customer/01-auth.html | Screen C-01e — Log in | Matches frame; tokens only; loading/error states | UI | design/screens/customer/01-auth.html | 1 | Not started |  | Not requested
136 |  |  |  | P2 App foundation + auth screens | Y | App-Customer | customer/01-auth.html | Screen C-01f — Log in · too many tries | Matches frame; tokens only; loading/error states | UI | design/screens/customer/01-auth.html | 1 | Not started |  | Not requested
137 |  |  |  | P2 App foundation + auth screens | Y | App-Customer | customer/01-auth.html | Screen C-01g — Check your email | Matches frame; tokens only; loading/error states | UI | design/screens/customer/01-auth.html | 1 | Not started |  | Not requested
138 |  |  |  | P2 App foundation + auth screens | Y | App-Customer | customer/01-auth.html | Screen C-01h — Forgot password | Matches frame; tokens only; loading/error states | UI | design/screens/customer/01-auth.html | 1 | Not started |  | Not requested
139 |  |  |  | P2 App foundation + auth screens | Y | App-Customer | customer/01-auth.html | Screen C-01i — Reset password | Matches frame; tokens only; loading/error states | UI | design/screens/customer/01-auth.html | 1 | Not started |  | Not requested
140 |  |  |  | P2 App foundation + auth screens | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
141 |  |  |  | P2 App foundation + auth screens | Y | App-Customer | customer/01-auth.html | Screen C-01j — Email verified | Matches frame; tokens only; loading/error states | UI | design/screens/customer/01-auth.html | 1 | Not started |  | Not requested
142 |  |  |  | P2 App foundation + auth screens | Y | App-Customer | customer/01-auth.html | Screen C-01k — Location permission | Matches frame; tokens only; loading/error states | UI | design/screens/customer/01-auth.html | 1 | Not started |  | Not requested
143 |  |  |  | P2 App foundation + auth screens | Y | App-Customer | customer/01-auth.html | Screen C-01l — Session expired | Matches frame; tokens only; loading/error states | UI | design/screens/customer/01-auth.html | 1 | Not started |  | Not requested
144 |  |  |  | P2 App foundation + auth screens | Y | App-Customer | customer/01-auth.html | Screen C-01m — Logged out from another device | Matches frame; tokens only; loading/error states | UI | design/screens/customer/01-auth.html | 1 | Not started |  | Not requested
145 |  |  |  | P2 App foundation + auth screens | Y | App-Customer | customer/01-auth.html | Screen C-01n — Account on hold | Matches frame; tokens only; loading/error states | UI | design/screens/customer/01-auth.html | 1 | Not started |  | Not requested
146 |  |  |  | P2 App foundation + auth screens | Y | App-Customer | customer/01-auth.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/customer/01-auth.html | 1 | Not started |  | Not requested
147 |  |  |  | P2 App foundation + auth screens | Y | App-Customer | customer/01-auth.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/customer/01-auth.html | 1 | Not started |  | Not requested
148 |  |  |  | P2 App foundation + auth screens | Y | Review | customer/01-auth.html | Review with Claude: customer/01-auth.html | All review comments fixed | Code review | design/screens/customer/01-auth.html | 1 | Not started |  | Not requested
149 |  |  |  | P2 App foundation + auth screens | Y | App-Worker | worker/01-signup.html | Screen W-01a — Splash | Matches frame; tokens only; loading/error states | UI | design/screens/worker/01-signup.html | 1 | Not started |  | Not requested
150 |  |  |  | P2 App foundation + auth screens | Y | App-Worker | worker/01-signup.html | Screen W-01b — Welcome + language | Matches frame; tokens only; loading/error states | UI | design/screens/worker/01-signup.html | 1 | Not started |  | Not requested
151 |  |  |  | P2 App foundation + auth screens | Y | App-Worker | worker/01-signup.html | Screen W-01c — Sign up | Matches frame; tokens only; loading/error states | UI | design/screens/worker/01-signup.html | 1 | Not started |  | Not requested
152 |  |  |  | P2 App foundation + auth screens | Y | App-Worker | worker/01-signup.html | Screen W-01d — Check your email | Matches frame; tokens only; loading/error states | UI | design/screens/worker/01-signup.html | 1 | Not started |  | Not requested
153 |  |  |  | P2 App foundation + auth screens | Y | App-Worker | worker/01-signup.html | Screen W-01e — Log in | Matches frame; tokens only; loading/error states | UI | design/screens/worker/01-signup.html | 1 | Not started |  | Not requested
154 |  |  |  | P2 App foundation + auth screens | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
155 |  |  |  | P2 App foundation + auth screens | Y | App-Worker | worker/01-signup.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/worker/01-signup.html | 1 | Not started |  | Not requested
156 |  |  |  | P2 App foundation + auth screens | Y | App-Worker | worker/01-signup.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/worker/01-signup.html | 1 | Not started |  | Not requested
157 |  |  |  | P2 App foundation + auth screens | Y | Review | worker/01-signup.html | Review with Claude: worker/01-signup.html | All review comments fixed | Code review | design/screens/worker/01-signup.html | 1 | Not started |  | Not requested
158 |  |  |  | P2 App foundation + auth screens | Y | App-Customer | customer/02-home.html | Screen C-02a — Home | Matches frame; tokens only; loading/error states | UI | design/screens/customer/02-home.html | 1 | Not started |  | Not requested
159 |  |  |  | P2 App foundation + auth screens | Y | App-Customer | customer/02-home.html | Screen C-02b — Saved-address picker | Matches frame; tokens only; loading/error states | UI | design/screens/customer/02-home.html | 1 | Not started |  | Not requested
160 |  |  |  | P2 App foundation + auth screens | Y | App-Customer | customer/02-home.html | Screen C-02c — Home · loading skeleton | Matches frame; tokens only; loading/error states | UI | design/screens/customer/02-home.html | 1 | Not started |  | Not requested
161 |  |  |  | P2 App foundation + auth screens | Y | App-Customer | customer/02-home.html | Screen C-02d — Catalog search · "pakha" | Matches frame; tokens only; loading/error states | UI | design/screens/customer/02-home.html | 1 | Not started |  | Not requested
162 |  |  |  | P2 App foundation + auth screens | Y | App-Customer | customer/02-home.html | Screen C-02f — Drafts list | Matches frame; tokens only; loading/error states | UI | design/screens/customer/02-home.html | 1 | Not started |  | Not requested
163 |  |  |  | P2 App foundation + auth screens | Y | App-Customer | customer/02-home.html | Screen C-02g — Tablet · customer home (768) | Matches frame; tokens only; loading/error states | UI | design/screens/customer/02-home.html | 1 | Not started |  | Not requested
164 |  |  |  | P2 App foundation + auth screens | Y | App-Customer | customer/02-home.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/customer/02-home.html | 1 | Not started |  | Not requested
165 |  |  |  | P2 App foundation + auth screens | Y | App-Customer | customer/02-home.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/customer/02-home.html | 1 | Not started |  | Not requested
166 |  |  |  | P2 App foundation + auth screens | Y | Review | customer/02-home.html | Review with Claude: customer/02-home.html | All review comments fixed | Code review | design/screens/customer/02-home.html | 1 | Not started |  | Not requested
167 |  |  |  | P2 App foundation + auth screens | Y | Review | milestone | Milestone demo: Customer + worker apps run on an Android phone; sign up, verify, log in, browse catalog | Demo recorded; README updated | Demo | plan/ | 1 | Not started |  | Not requested
168 |  |  |  | P3 Addresses, worker profile, media | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
169 |  |  |  | P3 Addresses, worker profile, media | Y | Learning | LLD-005 | Read LLD-005: Customer Address Book and Service-Area Check; list questions | Can explain the flow and tables | Domain | lld/lld-005-customer-addresses-service-zones.md | 1 | Not started |  | Not requested
170 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-005 | Flyway migration (1/3): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-005-customer-addresses-service-zones.md §3 | 1 | Not started |  | Not requested
171 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-005 | Flyway migration (2/3): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-005-customer-addresses-service-zones.md §3 | 1 | Not started |  | Not requested
172 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-005 | Flyway migration (3/3): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-005-customer-addresses-service-zones.md §3 | 1 | Not started |  | Not requested
173 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-005 | Entities + repositories (1/3) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-005-customer-addresses-service-zones.md §3 | 1 | Not started |  | Not requested
174 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-005 | Entities + repositories (2/3) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-005-customer-addresses-service-zones.md §3 | 1 | Not started |  | Not requested
175 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-005 | Entities + repositories (3/3) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-005-customer-addresses-service-zones.md §3 | 1 | Not started |  | Not requested
176 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-005 | PostGIS point + PIN zone check | Unit tests cover happy + failure paths | Domain logic | lld/lld-005-customer-addresses-service-zones.md §2/§5/§6 | 1 | Not started |  | Not requested
177 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-005 | Address snapshot copy for requests | Unit tests cover happy + failure paths | Domain logic | lld/lld-005-customer-addresses-service-zones.md §2/§5/§6 | 1 | Not started |  | Not requested
178 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-005 | Address limits + default address rules | Unit tests cover happy + failure paths | Domain logic | lld/lld-005-customer-addresses-service-zones.md §2/§5/§6 | 1 | Not started |  | Not requested
179 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-005 | API GET /api/v1/customer/addresses | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-005-customer-addresses-service-zones.md §4 | 1 | Not started |  | Not requested
180 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-005 | API POST /api/v1/customer/addresses | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-005-customer-addresses-service-zones.md §4 | 1 | Not started |  | Not requested
181 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-005 | API PATCH /api/v1/customer/addresses/{id} | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-005-customer-addresses-service-zones.md §4 | 1 | Not started |  | Not requested
182 |  |  |  | P3 Addresses, worker profile, media | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
183 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-005 | API DELETE /api/v1/customer/addresses/{id} | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-005-customer-addresses-service-zones.md §4 | 1 | Not started |  | Not requested
184 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-005 | API POST /api/v1/customer/addresses/{id}/default | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-005-customer-addresses-service-zones.md §4 | 1 | Not started |  | Not requested
185 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-005 | API GET /api/v1/service-areas/check | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-005-customer-addresses-service-zones.md §4 | 1 | Not started |  | Not requested
186 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-005 | API POST /api/v1/service-areas/waitlist | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-005-customer-addresses-service-zones.md §4 | 1 | Not started |  | Not requested
187 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-005 | API POST /api/v1/admin/service-zones[/{id}] | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-005-customer-addresses-service-zones.md §4 | 1 | Not started |  | Not requested
188 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-005 | API PUT /api/v1/admin/service-zones/{id}/pincodes | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-005-customer-addresses-service-zones.md §4 | 1 | Not started |  | Not requested
189 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-005 | API PUT /api/v1/admin/service-zones/{id}/boundary | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-005-customer-addresses-service-zones.md §4 | 1 | Not started |  | Not requested
190 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-005 | API POST /api/v1/admin/service-zones/{id}/status | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-005-customer-addresses-service-zones.md §4 | 1 | Not started |  | Not requested
191 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-005 | API GET /api/v1/admin/service-zones/waitlist | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-005-customer-addresses-service-zones.md §4 | 1 | Not started |  | Not requested
192 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-005 | Events: publish/consume via outbox; check error handling §7 | Outbox rows written; consumer idempotent | Events | lld/lld-005-customer-addresses-service-zones.md §7 | 1 | Not started |  | Not requested
193 |  |  |  | P3 Addresses, worker profile, media | Y | Review | LLD-005 | Module review with Claude: LLD-005 full diff + test plan §10 | All review comments fixed | Code review | lld/lld-005-customer-addresses-service-zones.md §10 | 1 | Not started |  | Not requested
194 |  |  |  | P3 Addresses, worker profile, media | Y | Learning | LLD-004 | Read LLD-004: Worker Profile — Trades, Rates, Skills and Job Readiness; list questions | Can explain the flow and tables | Domain | lld/lld-004-worker-profile-trades-rates.md | 1 | Not started |  | Not requested
195 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-004 | Flyway migration (1/3): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-004-worker-profile-trades-rates.md §3 | 1 | Not started |  | Not requested
196 |  |  |  | P3 Addresses, worker profile, media | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
197 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-004 | Flyway migration (2/3): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-004-worker-profile-trades-rates.md §3 | 1 | Not started |  | Not requested
198 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-004 | Flyway migration (3/3): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-004-worker-profile-trades-rates.md §3 | 1 | Not started |  | Not requested
199 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-004 | Entities + repositories (1/3) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-004-worker-profile-trades-rates.md §3 | 1 | Not started |  | Not requested
200 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-004 | Entities + repositories (2/3) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-004-worker-profile-trades-rates.md §3 | 1 | Not started |  | Not requested
201 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-004 | Entities + repositories (3/3) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-004-worker-profile-trades-rates.md §3 | 1 | Not started |  | Not requested
202 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-004 | Rate bounds validation per trade | Unit tests cover happy + failure paths | Domain logic | lld/lld-004-worker-profile-trades-rates.md §2/§5/§6 | 1 | Not started |  | Not requested
203 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-004 | Job readiness calculation (what blocks ACTIVE) | Unit tests cover happy + failure paths | Domain logic | lld/lld-004-worker-profile-trades-rates.md §2/§5/§6 | 1 | Not started |  | Not requested
204 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-004 | API GET /api/v1/workers/me | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-004-worker-profile-trades-rates.md §4 | 1 | Not started |  | Not requested
205 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-004 | API PATCH /api/v1/workers/me | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-004-worker-profile-trades-rates.md §4 | 1 | Not started |  | Not requested
206 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-004 | API PUT /api/v1/workers/me/professions | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-004-worker-profile-trades-rates.md §4 | 1 | Not started |  | Not requested
207 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-004 | API PUT /api/v1/workers/me/professions/{professionId}/rates | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-004-worker-profile-trades-rates.md §4 | 1 | Not started |  | Not requested
208 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-004 | API PUT /api/v1/workers/me/professions/{professionId}/skills | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-004-worker-profile-trades-rates.md §4 | 1 | Not started |  | Not requested
209 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-004 | API GET /api/v1/workers/me/readiness | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-004-worker-profile-trades-rates.md §4 | 1 | Not started |  | Not requested
210 |  |  |  | P3 Addresses, worker profile, media | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
211 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-004 | API GET /api/v1/workers/{workerId} | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-004-worker-profile-trades-rates.md §4 | 1 | Not started |  | Not requested
212 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-004 | Events: publish/consume via outbox; check error handling §7 | Outbox rows written; consumer idempotent | Events | lld/lld-004-worker-profile-trades-rates.md §7 | 1 | Not started |  | Not requested
213 |  |  |  | P3 Addresses, worker profile, media | Y | Review | LLD-004 | Module review with Claude: LLD-004 full diff + test plan §10 | All review comments fixed | Code review | lld/lld-004-worker-profile-trades-rates.md §10 | 1 | Not started |  | Not requested
214 |  |  |  | P3 Addresses, worker profile, media | Y | Learning | LLD-015 | Read LLD-015: Worker Availability — Working Hours, Time Off, Capacity; list questions | Can explain the flow and tables | Domain | lld/lld-015-worker-availability-schedule.md | 1 | Not started |  | Not requested
215 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-015 | Flyway migration: tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-015-worker-availability-schedule.md §3 | 1 | Not started |  | Not requested
216 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-015 | Entities + repositories + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-015-worker-availability-schedule.md §3 | 1 | Not started |  | Not requested
217 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-015 | Working hours + time off rules | Unit tests cover happy + failure paths | Domain logic | lld/lld-015-worker-availability-schedule.md §2/§5/§6 | 1 | Not started |  | Not requested
218 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-015 | Open-job capacity cap check used by matching | Unit tests cover happy + failure paths | Domain logic | lld/lld-015-worker-availability-schedule.md §2/§5/§6 | 1 | Not started |  | Not requested
219 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-015 | API GET /api/v1/workers/me/schedule | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-015-worker-availability-schedule.md §4 | 1 | Not started |  | Not requested
220 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-015 | API PUT /api/v1/workers/me/schedule/working-hours | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-015-worker-availability-schedule.md §4 | 1 | Not started |  | Not requested
221 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-015 | API PUT /api/v1/workers/me/schedule/capacity | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-015-worker-availability-schedule.md §4 | 1 | Not started |  | Not requested
222 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-015 | API POST /api/v1/workers/me/time-off | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-015-worker-availability-schedule.md §4 | 1 | Not started |  | Not requested
223 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-015 | API DELETE /api/v1/workers/me/time-off/{id} | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-015-worker-availability-schedule.md §4 | 1 | Not started |  | Not requested
224 |  |  |  | P3 Addresses, worker profile, media | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
225 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-015 | API GET /api/v1/admin/workers/{id}/schedule | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-015-worker-availability-schedule.md §4 | 1 | Not started |  | Not requested
226 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-015 | Events: publish/consume via outbox; check error handling §7 | Outbox rows written; consumer idempotent | Events | lld/lld-015-worker-availability-schedule.md §7 | 1 | Not started |  | Not requested
227 |  |  |  | P3 Addresses, worker profile, media | Y | Review | LLD-015 | Module review with Claude: LLD-015 full diff + test plan §10 | All review comments fixed | Code review | lld/lld-015-worker-availability-schedule.md §10 | 1 | Not started |  | Not requested
228 |  |  |  | P3 Addresses, worker profile, media | Y | Learning | LLD-014 | Read LLD-014: Media Upload and Object Storage; list questions | Can explain the flow and tables | Domain | lld/lld-014-media-upload.md | 1 | Not started |  | Not requested
229 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-014 | Flyway migration: tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-014-media-upload.md §3 | 1 | Not started |  | Not requested
230 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-014 | Entities + repositories + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-014-media-upload.md §3 | 1 | Not started |  | Not requested
231 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-014 | MinIO in docker-compose; S3 client config | Unit tests cover happy + failure paths | Domain logic | lld/lld-014-media-upload.md §2/§5/§6 | 1 | Not started |  | Not requested
232 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-014 | Presigned PUT upload intent + size/type limits | Unit tests cover happy + failure paths | Domain logic | lld/lld-014-media-upload.md §2/§5/§6 | 1 | Not started |  | Not requested
233 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-014 | Complete upload: verify object, attach-once rule | Unit tests cover happy + failure paths | Domain logic | lld/lld-014-media-upload.md §2/§5/§6 | 1 | Not started |  | Not requested
234 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-014 | API POST /api/v1/media/upload-intents | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-014-media-upload.md §4 | 1 | Not started |  | Not requested
235 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-014 | API POST /api/v1/media/{id}/complete | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-014-media-upload.md §4 | 1 | Not started |  | Not requested
236 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-014 | API GET /api/v1/media/{id} | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-014-media-upload.md §4 | 1 | Not started |  | Not requested
237 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-014 | API DELETE /api/v1/media/{id} | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-014-media-upload.md §4 | 1 | Not started |  | Not requested
238 |  |  |  | P3 Addresses, worker profile, media | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
239 |  |  |  | P3 Addresses, worker profile, media | Y | Backend | LLD-014 | Events: publish/consume via outbox; check error handling §7 | Outbox rows written; consumer idempotent | Events | lld/lld-014-media-upload.md §7 | 1 | Not started |  | Not requested
240 |  |  |  | P3 Addresses, worker profile, media | Y | Review | LLD-014 | Module review with Claude: LLD-014 full diff + test plan §10 | All review comments fixed | Code review | lld/lld-014-media-upload.md §10 | 1 | Not started |  | Not requested
241 |  |  |  | P3 Addresses, worker profile, media | Y | Learning | — | react-native-maps + expo-location: map pin, permissions | Notes in learning log; small sample committed | Maps |  | 1 | Not started |  | Not requested
242 |  |  |  | P3 Addresses, worker profile, media | Y | Learning | — | expo-image-picker + upload to presigned URL with progress | Notes in learning log; small sample committed | Uploads |  | 1 | Not started |  | Not requested
243 |  |  |  | P3 Addresses, worker profile, media | Y | App-Customer | customer/12-addresses.html | Screen C-12a — Saved addresses | Matches frame; tokens only; loading/error states | UI | design/screens/customer/12-addresses.html | 1 | Not started |  | Not requested
244 |  |  |  | P3 Addresses, worker profile, media | Y | App-Customer | customer/12-addresses.html | Screen C-12b — Add address · 1 Set the pin | Matches frame; tokens only; loading/error states | UI | design/screens/customer/12-addresses.html | 1 | Not started |  | Not requested
245 |  |  |  | P3 Addresses, worker profile, media | Y | App-Customer | customer/12-addresses.html | Screen C-12c — Add address · 2 Details | Matches frame; tokens only; loading/error states | UI | design/screens/customer/12-addresses.html | 1 | Not started |  | Not requested
246 |  |  |  | P3 Addresses, worker profile, media | Y | App-Customer | customer/12-addresses.html | Screen C-12d — Add address · 2 Details (cont.) | Matches frame; tokens only; loading/error states | UI | design/screens/customer/12-addresses.html | 1 | Not started |  | Not requested
247 |  |  |  | P3 Addresses, worker profile, media | Y | App-Customer | customer/12-addresses.html | Screen C-12e — Not in service area | Matches frame; tokens only; loading/error states | UI | design/screens/customer/12-addresses.html | 1 | Not started |  | Not requested
248 |  |  |  | P3 Addresses, worker profile, media | Y | App-Customer | customer/12-addresses.html | Screen C-12f — You're on the list | Matches frame; tokens only; loading/error states | UI | design/screens/customer/12-addresses.html | 1 | Not started |  | Not requested
249 |  |  |  | P3 Addresses, worker profile, media | Y | App-Customer | customer/12-addresses.html | Screen C-12g — Address saved outside zone | Matches frame; tokens only; loading/error states | UI | design/screens/customer/12-addresses.html | 1 | Not started |  | Not requested
250 |  |  |  | P3 Addresses, worker profile, media | Y | App-Customer | customer/12-addresses.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/customer/12-addresses.html | 1 | Not started |  | Not requested
251 |  |  |  | P3 Addresses, worker profile, media | Y | App-Customer | customer/12-addresses.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/customer/12-addresses.html | 1 | Not started |  | Not requested
252 |  |  |  | P3 Addresses, worker profile, media | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
253 |  |  |  | P3 Addresses, worker profile, media | Y | Review | customer/12-addresses.html | Review with Claude: customer/12-addresses.html | All review comments fixed | Code review | design/screens/customer/12-addresses.html | 1 | Not started |  | Not requested
254 |  |  |  | P3 Addresses, worker profile, media | Y | App-Worker | worker/02-onboarding.html | Screen W-02a — Readiness checklist | Matches frame; tokens only; loading/error states | UI | design/screens/worker/02-onboarding.html | 1 | Not started |  | Not requested
255 |  |  |  | P3 Addresses, worker profile, media | Y | App-Worker | worker/02-onboarding.html | Screen W-02c — Profile basics | Matches frame; tokens only; loading/error states | UI | design/screens/worker/02-onboarding.html | 1 | Not started |  | Not requested
256 |  |  |  | P3 Addresses, worker profile, media | Y | App-Worker | worker/02-onboarding.html | Screen W-02d — Trades | Matches frame; tokens only; loading/error states | UI | design/screens/worker/02-onboarding.html | 1 | Not started |  | Not requested
257 |  |  |  | P3 Addresses, worker profile, media | Y | App-Worker | worker/02-onboarding.html | Screen W-02f — Skills per trade | Matches frame; tokens only; loading/error states | UI | design/screens/worker/02-onboarding.html | 1 | Not started |  | Not requested
258 |  |  |  | P3 Addresses, worker profile, media | Y | App-Worker | worker/02-onboarding.html | Screen W-02g — Service area | Matches frame; tokens only; loading/error states | UI | design/screens/worker/02-onboarding.html | 1 | Not started |  | Not requested
259 |  |  |  | P3 Addresses, worker profile, media | Y | App-Worker | worker/02-onboarding.html | Screen W-02i — Working hours · custom | Matches frame; tokens only; loading/error states | UI | design/screens/worker/02-onboarding.html | 1 | Not started |  | Not requested
260 |  |  |  | P3 Addresses, worker profile, media | Y | App-Worker | worker/02-onboarding.html | Screen W-02j — Time off & capacity | Matches frame; tokens only; loading/error states | UI | design/screens/worker/02-onboarding.html | 1 | Not started |  | Not requested
261 |  |  |  | P3 Addresses, worker profile, media | Y | App-Worker | worker/02-onboarding.html | Screen W-02k — Emergency jobs opt-in | Matches frame; tokens only; loading/error states | UI | design/screens/worker/02-onboarding.html | 1 | Not started |  | Not requested
262 |  |  |  | P3 Addresses, worker profile, media | Y | App-Worker | worker/02-onboarding.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/worker/02-onboarding.html | 1 | Not started |  | Not requested
263 |  |  |  | P3 Addresses, worker profile, media | Y | App-Worker | worker/02-onboarding.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/worker/02-onboarding.html | 1 | Not started |  | Not requested
264 |  |  |  | P3 Addresses, worker profile, media | Y | Review | worker/02-onboarding.html | Review with Claude: worker/02-onboarding.html | All review comments fixed | Code review | design/screens/worker/02-onboarding.html | 1 | Not started |  | Not requested
265 |  |  |  | P3 Addresses, worker profile, media | Y | Review | milestone | Milestone demo: Customer saves an address with map pin; worker completes profile, trades, rates, hours, area and uploads photo | Demo recorded; README updated | Demo | plan/ | 1 | Not started |  | Not requested
266 |  |  |  | P4 Request & matching | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
267 |  |  |  | P4 Request & matching | Y | Learning | LLD-006 | Read LLD-006: Create Service Request (Problems, Urgency, Emergency, Drafts, Advance, Address Snapshot); list questions | Can explain the flow and tables | Domain | lld/lld-006-create-service-request.md | 1 | Not started |  | Not requested
268 |  |  |  | P4 Request & matching | Y | Backend | LLD-006 | Flyway migration (1/2): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-006-create-service-request.md §3 | 1 | Not started |  | Not requested
269 |  |  |  | P4 Request & matching | Y | Backend | LLD-006 | Flyway migration (2/2): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-006-create-service-request.md §3 | 1 | Not started |  | Not requested
270 |  |  |  | P4 Request & matching | Y | Backend | LLD-006 | Entities + repositories (1/2) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-006-create-service-request.md §3 | 1 | Not started |  | Not requested
271 |  |  |  | P4 Request & matching | Y | Backend | LLD-006 | Entities + repositories (2/2) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-006-create-service-request.md §3 | 1 | Not started |  | Not requested
272 |  |  |  | P4 Request & matching | Y | Backend | LLD-006 | Time window rules: NOW / TODAY / SCHEDULED | Unit tests cover happy + failure paths | Domain logic | lld/lld-006-create-service-request.md §2/§5/§6 | 1 | Not started |  | Not requested
273 |  |  |  | P4 Request & matching | Y | Backend | LLD-006 | Request state machine + cancel rules | Unit tests cover happy + failure paths | Domain logic | lld/lld-006-create-service-request.md §2/§5/§6 | 1 | Not started |  | Not requested
274 |  |  |  | P4 Request & matching | Y | Backend | LLD-006 | Quote preview (visit charge range) | Unit tests cover happy + failure paths | Domain logic | lld/lld-006-create-service-request.md §2/§5/§6 | 1 | Not started |  | Not requested
275 |  |  |  | P4 Request & matching | Y | Backend | LLD-006 | API POST /api/v1/service-requests | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-006-create-service-request.md §4 | 1 | Not started |  | Not requested
276 |  |  |  | P4 Request & matching | Y | Backend | LLD-006 | API GET /api/v1/service-requests/quote-preview | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-006-create-service-request.md §4 | 1 | Not started |  | Not requested
277 |  |  |  | P4 Request & matching | Y | Backend | LLD-006 | API GET /api/v1/service-requests | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-006-create-service-request.md §4 | 1 | Not started |  | Not requested
278 |  |  |  | P4 Request & matching | Y | Backend | LLD-006 | API GET /api/v1/service-requests/{id} | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-006-create-service-request.md §4 | 1 | Not started |  | Not requested
279 |  |  |  | P4 Request & matching | Y | Backend | LLD-006 | API POST /api/v1/service-requests/{id}/pay-advance | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-006-create-service-request.md §4 | 1 | Not started |  | Not requested
280 |  |  |  | P4 Request & matching | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
281 |  |  |  | P4 Request & matching | Y | Backend | LLD-006 | API POST /api/v1/service-requests/{id}/cancel | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-006-create-service-request.md §4 | 1 | Not started |  | Not requested
282 |  |  |  | P4 Request & matching | Y | Backend | LLD-006 | API GET /api/v1/service-requests/{id}/repeat-template | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-006-create-service-request.md §4 | 1 | Not started |  | Not requested
283 |  |  |  | P4 Request & matching | Y | Backend | LLD-006 | API POST /api/v1/service-request-drafts | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-006-create-service-request.md §4 | 1 | Not started |  | Not requested
284 |  |  |  | P4 Request & matching | Y | Backend | LLD-006 | API GET /api/v1/service-request-drafts | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-006-create-service-request.md §4 | 1 | Not started |  | Not requested
285 |  |  |  | P4 Request & matching | Y | Backend | LLD-006 | API POST /api/v1/service-request-drafts/{id}/submit | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-006-create-service-request.md §4 | 1 | Not started |  | Not requested
286 |  |  |  | P4 Request & matching | Y | Backend | LLD-006 | Events: publish/consume via outbox; check error handling §7 | Outbox rows written; consumer idempotent | Events | lld/lld-006-create-service-request.md §7 | 1 | Not started |  | Not requested
287 |  |  |  | P4 Request & matching | Y | Review | LLD-006 | Module review with Claude: LLD-006 full diff + test plan §10 | All review comments fixed | Code review | lld/lld-006-create-service-request.md §10 | 1 | Not started |  | Not requested
288 |  |  |  | P4 Request & matching | Y | Learning | LLD-007 | Read LLD-007: Matching — Service Area, Online Status, Candidate Search and Rounds; list questions | Can explain the flow and tables | Domain | lld/lld-007-matching-candidate-search.md | 1 | Not started |  | Not requested
289 |  |  |  | P4 Request & matching | Y | Backend | LLD-007 | Flyway migration (1/3): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-007-matching-candidate-search.md §3 | 1 | Not started |  | Not requested
290 |  |  |  | P4 Request & matching | Y | Backend | LLD-007 | Flyway migration (2/3): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-007-matching-candidate-search.md §3 | 1 | Not started |  | Not requested
291 |  |  |  | P4 Request & matching | Y | Backend | LLD-007 | Flyway migration (3/3): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-007-matching-candidate-search.md §3 | 1 | Not started |  | Not requested
292 |  |  |  | P4 Request & matching | Y | Backend | LLD-007 | Entities + repositories (1/3) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-007-matching-candidate-search.md §3 | 1 | Not started |  | Not requested
293 |  |  |  | P4 Request & matching | Y | Backend | LLD-007 | Entities + repositories (2/3) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-007-matching-candidate-search.md §3 | 1 | Not started |  | Not requested
294 |  |  |  | P4 Request & matching | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
295 |  |  |  | P4 Request & matching | Y | Backend | LLD-007 | Entities + repositories (3/3) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-007-matching-candidate-search.md §3 | 1 | Not started |  | Not requested
296 |  |  |  | P4 Request & matching | Y | Backend | LLD-007 | Service area: base point + radius (PostGIS geography) | Unit tests cover happy + failure paths | Domain logic | lld/lld-007-matching-candidate-search.md §2/§5/§6 | 1 | Not started |  | Not requested
297 |  |  |  | P4 Request & matching | Y | Backend | LLD-007 | Online toggle + last-seen | Unit tests cover happy + failure paths | Domain logic | lld/lld-007-matching-candidate-search.md §2/§5/§6 | 1 | Not started |  | Not requested
298 |  |  |  | P4 Request & matching | Y | Backend | LLD-007 | Candidate query: distance, trade, rate, availability, dues | Unit tests cover happy + failure paths | Domain logic | lld/lld-007-matching-candidate-search.md §2/§5/§6 | 1 | Not started |  | Not requested
299 |  |  |  | P4 Request & matching | Y | Backend | LLD-007 | Matching rounds job: widen radius by schedule | Unit tests cover happy + failure paths | Domain logic | lld/lld-007-matching-candidate-search.md §2/§5/§6 | 1 | Not started |  | Not requested
300 |  |  |  | P4 Request & matching | Y | Backend | LLD-007 | Explainable score fields stored per match (ADR 0011) | Unit tests cover happy + failure paths | Domain logic | lld/lld-007-matching-candidate-search.md §2/§5/§6 | 1 | Not started |  | Not requested
301 |  |  |  | P4 Request & matching | Y | Backend | LLD-007 | Matching integration test with real PostGIS data | Unit tests cover happy + failure paths | Domain logic | lld/lld-007-matching-candidate-search.md §2/§5/§6 | 1 | Not started |  | Not requested
302 |  |  |  | P4 Request & matching | Y | Backend | LLD-007 | API PUT /api/v1/workers/me/service-area | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-007-matching-candidate-search.md §4 | 1 | Not started |  | Not requested
303 |  |  |  | P4 Request & matching | Y | Backend | LLD-007 | API GET /api/v1/workers/me/service-area | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-007-matching-candidate-search.md §4 | 1 | Not started |  | Not requested
304 |  |  |  | P4 Request & matching | Y | Backend | LLD-007 | API PUT /api/v1/workers/me/online | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-007-matching-candidate-search.md §4 | 1 | Not started |  | Not requested
305 |  |  |  | P4 Request & matching | Y | Backend | LLD-007 | API GET /api/v1/service-requests/{id}/matching | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-007-matching-candidate-search.md §4 | 1 | Not started |  | Not requested
306 |  |  |  | P4 Request & matching | Y | Backend | LLD-007 | API POST /api/v1/service-requests/{id}/search-again | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-007-matching-candidate-search.md §4 | 1 | Not started |  | Not requested
307 |  |  |  | P4 Request & matching | Y | Backend | LLD-007 | API GET /api/v1/service-areas/emergency-availability | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-007-matching-candidate-search.md §4 | 1 | Not started |  | Not requested
308 |  |  |  | P4 Request & matching | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
309 |  |  |  | P4 Request & matching | Y | Backend | LLD-007 | Events: publish/consume via outbox; check error handling §7 | Outbox rows written; consumer idempotent | Events | lld/lld-007-matching-candidate-search.md §7 | 1 | Not started |  | Not requested
310 |  |  |  | P4 Request & matching | Y | Review | LLD-007 | Module review with Claude: LLD-007 full diff + test plan §10 | All review comments fixed | Code review | lld/lld-007-matching-candidate-search.md §10 | 1 | Not started |  | Not requested
311 |  |  |  | P4 Request & matching | Y | Learning | LLD-008 | Read LLD-008: Worker Job Inbox (Accept / Decline / Withdraw), Customer Shortlist and Worker Selection; list questions | Can explain the flow and tables | Domain | lld/lld-008-offers-shortlist-selection.md | 1 | Not started |  | Not requested
312 |  |  |  | P4 Request & matching | Y | Backend | LLD-008 | Offer accept/decline/withdraw state machine | Unit tests cover happy + failure paths | Domain logic | lld/lld-008-offers-shortlist-selection.md §2/§5/§6 | 1 | Not started |  | Not requested
313 |  |  |  | P4 Request & matching | Y | Backend | LLD-008 | Shortlist ordering for the customer | Unit tests cover happy + failure paths | Domain logic | lld/lld-008-offers-shortlist-selection.md §2/§5/§6 | 1 | Not started |  | Not requested
314 |  |  |  | P4 Request & matching | Y | Backend | LLD-008 | Select worker → booking created event | Unit tests cover happy + failure paths | Domain logic | lld/lld-008-offers-shortlist-selection.md §2/§5/§6 | 1 | Not started |  | Not requested
315 |  |  |  | P4 Request & matching | Y | Backend | LLD-008 | API GET /api/v1/workers/me/offers | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-008-offers-shortlist-selection.md §4 | 1 | Not started |  | Not requested
316 |  |  |  | P4 Request & matching | Y | Backend | LLD-008 | API GET /api/v1/workers/me/offers/{matchId} | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-008-offers-shortlist-selection.md §4 | 1 | Not started |  | Not requested
317 |  |  |  | P4 Request & matching | Y | Backend | LLD-008 | API POST /api/v1/workers/me/offers/{matchId}/accept | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-008-offers-shortlist-selection.md §4 | 1 | Not started |  | Not requested
318 |  |  |  | P4 Request & matching | Y | Backend | LLD-008 | API POST /api/v1/workers/me/offers/{matchId}/decline | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-008-offers-shortlist-selection.md §4 | 1 | Not started |  | Not requested
319 |  |  |  | P4 Request & matching | Y | Backend | LLD-008 | API POST /api/v1/workers/me/offers/{matchId}/withdraw | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-008-offers-shortlist-selection.md §4 | 1 | Not started |  | Not requested
320 |  |  |  | P4 Request & matching | Y | Backend | LLD-008 | API GET /api/v1/service-requests/{id}/shortlist | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-008-offers-shortlist-selection.md §4 | 1 | Not started |  | Not requested
321 |  |  |  | P4 Request & matching | Y | Backend | LLD-008 | API POST /api/v1/service-requests/{id}/select-worker | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-008-offers-shortlist-selection.md §4 | 1 | Not started |  | Not requested
322 |  |  |  | P4 Request & matching | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
323 |  |  |  | P4 Request & matching | Y | Backend | LLD-008 | Events: publish/consume via outbox; check error handling §7 | Outbox rows written; consumer idempotent | Events | lld/lld-008-offers-shortlist-selection.md §7 | 1 | Not started |  | Not requested
324 |  |  |  | P4 Request & matching | Y | Review | LLD-008 | Module review with Claude: LLD-008 full diff + test plan §10 | All review comments fixed | Code review | lld/lld-008-offers-shortlist-selection.md §10 | 1 | Not started |  | Not requested
325 |  |  |  | P4 Request & matching | Y | App-Customer | customer/03-request.html | Screen C-03a — Step 1 · What — problems | Matches frame; tokens only; loading/error states | UI | design/screens/customer/03-request.html | 1 | Not started |  | Not requested
326 |  |  |  | P4 Request & matching | Y | App-Customer | customer/03-request.html | Screen C-03b — Step 1 · What — details & media | Matches frame; tokens only; loading/error states | UI | design/screens/customer/03-request.html | 1 | Not started |  | Not requested
327 |  |  |  | P4 Request & matching | Y | App-Customer | customer/03-request.html | Screen C-03c — Step 2 · Where & when | Matches frame; tokens only; loading/error states | UI | design/screens/customer/03-request.html | 1 | Not started |  | Not requested
328 |  |  |  | P4 Request & matching | Y | App-Customer | customer/03-request.html | Screen C-03d — Step 2 · Emergency (11:40 PM) | Matches frame; tokens only; loading/error states | UI | design/screens/customer/03-request.html | 1 | Not started |  | Not requested
329 |  |  |  | P4 Request & matching | Y | App-Customer | customer/03-request.html | Screen C-03e — Error · same job already open | Matches frame; tokens only; loading/error states | UI | design/screens/customer/03-request.html | 1 | Not started |  | Not requested
330 |  |  |  | P4 Request & matching | Y | App-Customer | customer/03-request.html | Screen C-03f — Error · 3 open requests | Matches frame; tokens only; loading/error states | UI | design/screens/customer/03-request.html | 1 | Not started |  | Not requested
331 |  |  |  | P4 Request & matching | Y | App-Customer | customer/03-request.html | Screen C-03g — Error · not in service area | Matches frame; tokens only; loading/error states | UI | design/screens/customer/03-request.html | 1 | Not started |  | Not requested
332 |  |  |  | P4 Request & matching | Y | App-Customer | customer/03-request.html | Screen C-03h — Step 3 · Confirm & pay advance | Matches frame; tokens only; loading/error states | UI | design/screens/customer/03-request.html | 1 | Not started |  | Not requested
333 |  |  |  | P4 Request & matching | Y | App-Customer | customer/03-request.html | Screen C-03i — Step 3 · Confirm (emergency) | Matches frame; tokens only; loading/error states | UI | design/screens/customer/03-request.html | 1 | Not started |  | Not requested
334 |  |  |  | P4 Request & matching | Y | App-Customer | customer/03-request.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/customer/03-request.html | 1 | Not started |  | Not requested
335 |  |  |  | P4 Request & matching | Y | App-Customer | customer/03-request.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/customer/03-request.html | 1 | Not started |  | Not requested
336 |  |  |  | P4 Request & matching | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
337 |  |  |  | P4 Request & matching | Y | Review | customer/03-request.html | Review with Claude: customer/03-request.html | All review comments fixed | Code review | design/screens/customer/03-request.html | 1 | Not started |  | Not requested
338 |  |  |  | P4 Request & matching | Y | App-Customer | customer/05-matching.html | Screen C-05a — Matching in progress | Matches frame; tokens only; loading/error states | UI | design/screens/customer/05-matching.html | 1 | Not started |  | Not requested
339 |  |  |  | P4 Request & matching | Y | App-Customer | customer/05-matching.html | Screen C-05b — Matching · held until 7 AM | Matches frame; tokens only; loading/error states | UI | design/screens/customer/05-matching.html | 1 | Not started |  | Not requested
340 |  |  |  | P4 Request & matching | Y | App-Customer | customer/05-matching.html | Screen C-05c — Workers found · shortlist | Matches frame; tokens only; loading/error states | UI | design/screens/customer/05-matching.html | 1 | Not started |  | Not requested
341 |  |  |  | P4 Request & matching | Y | App-Customer | customer/05-matching.html | Screen C-05d — Select confirm sheet | Matches frame; tokens only; loading/error states | UI | design/screens/customer/05-matching.html | 1 | Not started |  | Not requested
342 |  |  |  | P4 Request & matching | Y | App-Customer | customer/05-matching.html | Screen C-05e — Worker profile (from shortlist) | Matches frame; tokens only; loading/error states | UI | design/screens/customer/05-matching.html | 1 | Not started |  | Not requested
343 |  |  |  | P4 Request & matching | Y | App-Customer | customer/05-matching.html | Screen C-05f — All worker reviews | Matches frame; tokens only; loading/error states | UI | design/screens/customer/05-matching.html | 1 | Not started |  | Not requested
344 |  |  |  | P4 Request & matching | Y | App-Customer | customer/05-matching.html | Screen C-05g — No workers found | Matches frame; tokens only; loading/error states | UI | design/screens/customer/05-matching.html | 1 | Not started |  | Not requested
345 |  |  |  | P4 Request & matching | Y | App-Customer | customer/05-matching.html | Screen C-05h — Cancel request (before booking) | Matches frame; tokens only; loading/error states | UI | design/screens/customer/05-matching.html | 1 | Not started |  | Not requested
346 |  |  |  | P4 Request & matching | Y | App-Customer | customer/05-matching.html | Screen C-05i — Request cancelled · refund | Matches frame; tokens only; loading/error states | UI | design/screens/customer/05-matching.html | 1 | Not started |  | Not requested
347 |  |  |  | P4 Request & matching | Y | App-Customer | customer/05-matching.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/customer/05-matching.html | 1 | Not started |  | Not requested
348 |  |  |  | P4 Request & matching | Y | App-Customer | customer/05-matching.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/customer/05-matching.html | 1 | Not started |  | Not requested
349 |  |  |  | P4 Request & matching | Y | Review | customer/05-matching.html | Review with Claude: customer/05-matching.html | All review comments fixed | Code review | design/screens/customer/05-matching.html | 1 | Not started |  | Not requested
350 |  |  |  | P4 Request & matching | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
351 |  |  |  | P4 Request & matching | Y | App-Worker | worker/05-home-offers.html | Screen W-05a — Worker home · ready | Matches frame; tokens only; loading/error states | UI | design/screens/worker/05-home-offers.html | 1 | Not started |  | Not requested
352 |  |  |  | P4 Request & matching | Y | App-Worker | worker/05-home-offers.html | Screen W-05b — Worker home · Bengali | Matches frame; tokens only; loading/error states | UI | design/screens/worker/05-home-offers.html | 1 | Not started |  | Not requested
353 |  |  |  | P4 Request & matching | Y | App-Worker | worker/05-home-offers.html | Screen W-05c — Worker home · not ready yet | Matches frame; tokens only; loading/error states | UI | design/screens/worker/05-home-offers.html | 1 | Not started |  | Not requested
354 |  |  |  | P4 Request & matching | Y | App-Worker | worker/05-home-offers.html | Screen W-05d — Worker home · dues over limit | Matches frame; tokens only; loading/error states | UI | design/screens/worker/05-home-offers.html | 1 | Not started |  | Not requested
355 |  |  |  | P4 Request & matching | Y | App-Worker | worker/05-home-offers.html | Screen W-05e — Offers inbox · New | Matches frame; tokens only; loading/error states | UI | design/screens/worker/05-home-offers.html | 1 | Not started |  | Not requested
356 |  |  |  | P4 Request & matching | Y | App-Worker | worker/05-home-offers.html | Screen W-05f — Offers · Waiting for customer | Matches frame; tokens only; loading/error states | UI | design/screens/worker/05-home-offers.html | 1 | Not started |  | Not requested
357 |  |  |  | P4 Request & matching | Y | App-Worker | worker/05-home-offers.html | Screen W-05g — Offer detail | Matches frame; tokens only; loading/error states | UI | design/screens/worker/05-home-offers.html | 1 | Not started |  | Not requested
358 |  |  |  | P4 Request & matching | Y | App-Worker | worker/05-home-offers.html | Screen W-05h — "I'm interested" sheet | Matches frame; tokens only; loading/error states | UI | design/screens/worker/05-home-offers.html | 1 | Not started |  | Not requested
359 |  |  |  | P4 Request & matching | Y | App-Worker | worker/05-home-offers.html | Screen W-05i — "I'm interested" sheet · Bengali | Matches frame; tokens only; loading/error states | UI | design/screens/worker/05-home-offers.html | 1 | Not started |  | Not requested
360 |  |  |  | P4 Request & matching | Y | App-Worker | worker/05-home-offers.html | Screen W-05j — Decline reason | Matches frame; tokens only; loading/error states | UI | design/screens/worker/05-home-offers.html | 1 | Not started |  | Not requested
361 |  |  |  | P4 Request & matching | Y | App-Worker | worker/05-home-offers.html | Screen W-05k — Not selected / request ended | Matches frame; tokens only; loading/error states | UI | design/screens/worker/05-home-offers.html | 1 | Not started |  | Not requested
362 |  |  |  | P4 Request & matching | Y | App-Worker | worker/05-home-offers.html | Screen W-05l — No offers · why (offline) | Matches frame; tokens only; loading/error states | UI | design/screens/worker/05-home-offers.html | 1 | Not started |  | Not requested
363 |  |  |  | P4 Request & matching | Y | App-Worker | worker/05-home-offers.html | Screen W-05m — No offers · outside hours | Matches frame; tokens only; loading/error states | UI | design/screens/worker/05-home-offers.html | 1 | Not started |  | Not requested
364 |  |  |  | P4 Request & matching | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
365 |  |  |  | P4 Request & matching | Y | App-Worker | worker/05-home-offers.html | Screen W-05n — Restricted · strikes | Matches frame; tokens only; loading/error states | UI | design/screens/worker/05-home-offers.html | 1 | Not started |  | Not requested
366 |  |  |  | P4 Request & matching | Y | App-Worker | worker/05-home-offers.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/worker/05-home-offers.html | 1 | Not started |  | Not requested
367 |  |  |  | P4 Request & matching | Y | App-Worker | worker/05-home-offers.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/worker/05-home-offers.html | 1 | Not started |  | Not requested
368 |  |  |  | P4 Request & matching | Y | Review | worker/05-home-offers.html | Review with Claude: worker/05-home-offers.html | All review comments fixed | Code review | design/screens/worker/05-home-offers.html | 1 | Not started |  | Not requested
369 |  |  |  | P4 Request & matching | Y | Review | milestone | Milestone demo: Customer posts a request → nearby workers get offers → say interested → customer picks one | Demo recorded; README updated | Demo | plan/ | 1 | Not started |  | Not requested
370 |  |  |  | P5 Booking & job | Y | Learning | LLD-009 | Read LLD-009: Booking, Job and Visits — Start Code, Check-in/out, Extra Days, Cancellations, No-shows, Completion; list questions | Can explain the flow and tables | Domain | lld/lld-009-booking-job-visits.md | 1 | Not started |  | Not requested
371 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | Flyway migration (1/3): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-009-booking-job-visits.md §3 | 1 | Not started |  | Not requested
372 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | Flyway migration (2/3): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-009-booking-job-visits.md §3 | 1 | Not started |  | Not requested
373 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | Flyway migration (3/3): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-009-booking-job-visits.md §3 | 1 | Not started |  | Not requested
374 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | Entities + repositories (1/3) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-009-booking-job-visits.md §3 | 1 | Not started |  | Not requested
375 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | Entities + repositories (2/3) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-009-booking-job-visits.md §3 | 1 | Not started |  | Not requested
376 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | Entities + repositories (3/3) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-009-booking-job-visits.md §3 | 1 | Not started |  | Not requested
377 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | Booking/job/visit state machines (architecture/04) | Unit tests cover happy + failure paths | Domain logic | lld/lld-009-booking-job-visits.md §2/§5/§6 | 1 | Not started |  | Not requested
378 |  |  |  | P5 Booking & job | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
379 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | Start code: generate, 5 tries, lockout | Unit tests cover happy + failure paths | Domain logic | lld/lld-009-booking-job-visits.md §2/§5/§6 | 1 | Not started |  | Not requested
380 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | Check-in with GPS distance check | Unit tests cover happy + failure paths | Domain logic | lld/lld-009-booking-job-visits.md §2/§5/§6 | 1 | Not started |  | Not requested
381 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | Check-out + amount calc: VISIT / HOURLY / DAILY | Unit tests cover happy + failure paths | Domain logic | lld/lld-009-booking-job-visits.md §2/§5/§6 | 1 | Not started |  | Not requested
382 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | Completion confirm + 24 h auto-confirm job | Unit tests cover happy + failure paths | Domain logic | lld/lld-009-booking-job-visits.md §2/§5/§6 | 1 | Not started |  | Not requested
383 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | Cancellation rules (2 h rule) + reason codes | Unit tests cover happy + failure paths | Domain logic | lld/lld-009-booking-job-visits.md §2/§5/§6 | 1 | Not started |  | Not requested
384 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | Worker no-show + customer no-show handling | Unit tests cover happy + failure paths | Domain logic | lld/lld-009-booking-job-visits.md §2/§5/§6 | 1 | Not started |  | Not requested
385 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | FAILED job → visit charge only | Unit tests cover happy + failure paths | Domain logic | lld/lld-009-booking-job-visits.md §2/§5/§6 | 1 | Not started |  | Not requested
386 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | Extra day / multi-day visits | Unit tests cover happy + failure paths | Domain logic | lld/lld-009-booking-job-visits.md §2/§5/§6 | 1 | Not started |  | Not requested
387 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | Booking timeline read model | Unit tests cover happy + failure paths | Domain logic | lld/lld-009-booking-job-visits.md §2/§5/§6 | 1 | Not started |  | Not requested
388 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | API GET /api/v1/bookings | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-009-booking-job-visits.md §4 | 1 | Not started |  | Not requested
389 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | API GET /api/v1/bookings/{id} | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-009-booking-job-visits.md §4 | 1 | Not started |  | Not requested
390 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | API POST /api/v1/visits/{id}/en-route | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-009-booking-job-visits.md §4 | 1 | Not started |  | Not requested
391 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | API POST /api/v1/visits/{id}/check-in | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-009-booking-job-visits.md §4 | 1 | Not started |  | Not requested
392 |  |  |  | P5 Booking & job | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
393 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | API GET /api/v1/visits/{id}/start-code | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-009-booking-job-visits.md §4 | 1 | Not started |  | Not requested
394 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | API POST /api/v1/visits/{id}/start-code/regenerate | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-009-booking-job-visits.md §4 | 1 | Not started |  | Not requested
395 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | API POST /api/v1/visits/{id}/start | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-009-booking-job-visits.md §4 | 1 | Not started |  | Not requested
396 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | API POST /api/v1/visits/{id}/check-out | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-009-booking-job-visits.md §4 | 1 | Not started |  | Not requested
397 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | API POST /api/v1/visits/{id}/confirm | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-009-booking-job-visits.md §4 | 1 | Not started |  | Not requested
398 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | API POST /api/v1/visits/{id}/report-worker-no-show | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-009-booking-job-visits.md §4 | 1 | Not started |  | Not requested
399 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | API POST /api/v1/visits/{id}/customer-no-show | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-009-booking-job-visits.md §4 | 1 | Not started |  | Not requested
400 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | API POST /api/v1/jobs/{id}/proposals | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-009-booking-job-visits.md §4 | 1 | Not started |  | Not requested
401 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | API POST /api/v1/proposals/{id}/accept | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-009-booking-job-visits.md §4 | 1 | Not started |  | Not requested
402 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | API POST /api/v1/bookings/{id}/cancel | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-009-booking-job-visits.md §4 | 1 | Not started |  | Not requested
403 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | API POST /api/v1/jobs/{id}/complete | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-009-booking-job-visits.md §4 | 1 | Not started |  | Not requested
404 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | API POST /api/v1/jobs/{id}/confirm-completion | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-009-booking-job-visits.md §4 | 1 | Not started |  | Not requested
405 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | API POST /api/v1/jobs/{id}/cannot-complete | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-009-booking-job-visits.md §4 | 1 | Not started |  | Not requested
406 |  |  |  | P5 Booking & job | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
407 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | API GET /api/v1/jobs/{id}/bill | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-009-booking-job-visits.md §4 | 1 | Not started |  | Not requested
408 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | API GET /api/v1/admin/bookings | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-009-booking-job-visits.md §4 | 1 | Not started |  | Not requested
409 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | API POST /api/v1/admin/bookings/{id}/cancel | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-009-booking-job-visits.md §4 | 1 | Not started |  | Not requested
410 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | API POST /api/v1/disputes | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-009-booking-job-visits.md §4 | 1 | Not started |  | Not requested
411 |  |  |  | P5 Booking & job | Y | Backend | LLD-009 | Events: publish/consume via outbox; check error handling §7 | Outbox rows written; consumer idempotent | Events | lld/lld-009-booking-job-visits.md §7 | 1 | Not started |  | Not requested
412 |  |  |  | P5 Booking & job | Y | Review | LLD-009 | Module review with Claude: LLD-009 full diff + test plan §10 | All review comments fixed | Code review | lld/lld-009-booking-job-visits.md §10 | 1 | Not started |  | Not requested
413 |  |  |  | P5 Booking & job | Y | App-Customer | customer/06-booking.html | Screen C-06a — Booking confirmed | Matches frame; tokens only; loading/error states | UI | design/screens/customer/06-booking.html | 1 | Not started |  | Not requested
414 |  |  |  | P5 Booking & job | Y | App-Customer | customer/06-booking.html | Screen C-06b — Bookings | Matches frame; tokens only; loading/error states | UI | design/screens/customer/06-booking.html | 1 | Not started |  | Not requested
415 |  |  |  | P5 Booking & job | Y | App-Customer | customer/06-booking.html | Screen C-06c — Booking detail | Matches frame; tokens only; loading/error states | UI | design/screens/customer/06-booking.html | 1 | Not started |  | Not requested
416 |  |  |  | P5 Booking & job | Y | App-Customer | customer/06-booking.html | Screen C-06d — Cancel booking | Matches frame; tokens only; loading/error states | UI | design/screens/customer/06-booking.html | 1 | Not started |  | Not requested
417 |  |  |  | P5 Booking & job | Y | App-Customer | customer/06-booking.html | Screen C-06e — Booking cancelled | Matches frame; tokens only; loading/error states | UI | design/screens/customer/06-booking.html | 1 | Not started |  | Not requested
418 |  |  |  | P5 Booking & job | Y | App-Customer | customer/06-booking.html | Screen C-06f — Ask to reschedule | Matches frame; tokens only; loading/error states | UI | design/screens/customer/06-booking.html | 1 | Not started |  | Not requested
419 |  |  |  | P5 Booking & job | Y | App-Customer | customer/06-booking.html | Screen C-06g — Add days / reschedule — respond | Matches frame; tokens only; loading/error states | UI | design/screens/customer/06-booking.html | 1 | Not started |  | Not requested
420 |  |  |  | P5 Booking & job | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
421 |  |  |  | P5 Booking & job | Y | App-Customer | customer/06-booking.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/customer/06-booking.html | 1 | Not started |  | Not requested
422 |  |  |  | P5 Booking & job | Y | App-Customer | customer/06-booking.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/customer/06-booking.html | 1 | Not started |  | Not requested
423 |  |  |  | P5 Booking & job | Y | Review | customer/06-booking.html | Review with Claude: customer/06-booking.html | All review comments fixed | Code review | design/screens/customer/06-booking.html | 1 | Not started |  | Not requested
424 |  |  |  | P5 Booking & job | Y | App-Customer | customer/07-job-tracking.html | Screen C-07a — Worker on the way | Matches frame; tokens only; loading/error states | UI | design/screens/customer/07-job-tracking.html | 1 | Not started |  | Not requested
425 |  |  |  | P5 Booking & job | Y | App-Customer | customer/07-job-tracking.html | Screen C-07b — Arrived — show start code | Matches frame; tokens only; loading/error states | UI | design/screens/customer/07-job-tracking.html | 1 | Not started |  | Not requested
426 |  |  |  | P5 Booking & job | Y | App-Customer | customer/07-job-tracking.html | Screen C-07c — Start code locked | Matches frame; tokens only; loading/error states | UI | design/screens/customer/07-job-tracking.html | 1 | Not started |  | Not requested
427 |  |  |  | P5 Booking & job | Y | App-Customer | customer/07-job-tracking.html | Screen C-07d — Work in progress | Matches frame; tokens only; loading/error states | UI | design/screens/customer/07-job-tracking.html | 1 | Not started |  | Not requested
428 |  |  |  | P5 Booking & job | Y | App-Customer | customer/07-job-tracking.html | Screen C-07e — Multi-day · Day 2 of 3 | Matches frame; tokens only; loading/error states | UI | design/screens/customer/07-job-tracking.html | 1 | Not started |  | Not requested
429 |  |  |  | P5 Booking & job | Y | App-Customer | customer/07-job-tracking.html | Screen C-07f — Confirm today's work | Matches frame; tokens only; loading/error states | UI | design/screens/customer/07-job-tracking.html | 1 | Not started |  | Not requested
430 |  |  |  | P5 Booking & job | Y | App-Customer | customer/07-job-tracking.html | Screen C-07g — Worker didn't come | Matches frame; tokens only; loading/error states | UI | design/screens/customer/07-job-tracking.html | 1 | Not started |  | Not requested
431 |  |  |  | P5 Booking & job | Y | App-Customer | customer/07-job-tracking.html | Screen C-07h — Quote approval | Matches frame; tokens only; loading/error states | UI | design/screens/customer/07-job-tracking.html | 1 | Not started |  | Not requested
432 |  |  |  | P5 Booking & job | Y | App-Customer | customer/07-job-tracking.html | Screen C-07i — Material bill — acknowledge | Matches frame; tokens only; loading/error states | UI | design/screens/customer/07-job-tracking.html | 1 | Not started |  | Not requested
433 |  |  |  | P5 Booking & job | Y | App-Customer | customer/07-job-tracking.html | Screen C-07j — Work done — confirm or report | Matches frame; tokens only; loading/error states | UI | design/screens/customer/07-job-tracking.html | 1 | Not started |  | Not requested
434 |  |  |  | P5 Booking & job | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
435 |  |  |  | P5 Booking & job | Y | App-Customer | customer/07-job-tracking.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/customer/07-job-tracking.html | 1 | Not started |  | Not requested
436 |  |  |  | P5 Booking & job | Y | App-Customer | customer/07-job-tracking.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/customer/07-job-tracking.html | 1 | Not started |  | Not requested
437 |  |  |  | P5 Booking & job | Y | Review | customer/07-job-tracking.html | Review with Claude: customer/07-job-tracking.html | All review comments fixed | Code review | design/screens/customer/07-job-tracking.html | 1 | Not started |  | Not requested
438 |  |  |  | P5 Booking & job | Y | App-Worker | worker/06-job-flow.html | Screen W-06a — Jobs · Today | Matches frame; tokens only; loading/error states | UI | design/screens/worker/06-job-flow.html | 1 | Not started |  | Not requested
439 |  |  |  | P5 Booking & job | Y | App-Worker | worker/06-job-flow.html | Screen W-06b — Jobs · Waiting for customer | Matches frame; tokens only; loading/error states | UI | design/screens/worker/06-job-flow.html | 1 | Not started |  | Not requested
440 |  |  |  | P5 Booking & job | Y | App-Worker | worker/06-job-flow.html | Screen W-06c — Jobs · Upcoming | Matches frame; tokens only; loading/error states | UI | design/screens/worker/06-job-flow.html | 1 | Not started |  | Not requested
441 |  |  |  | P5 Booking & job | Y | App-Worker | worker/06-job-flow.html | Screen W-06d — Jobs · Done | Matches frame; tokens only; loading/error states | UI | design/screens/worker/06-job-flow.html | 1 | Not started |  | Not requested
442 |  |  |  | P5 Booking & job | Y | App-Worker | worker/06-job-flow.html | Screen W-06e — Booking detail | Matches frame; tokens only; loading/error states | UI | design/screens/worker/06-job-flow.html | 1 | Not started |  | Not requested
443 |  |  |  | P5 Booking & job | Y | App-Worker | worker/06-job-flow.html | Screen W-06f — On my way + ETA | Matches frame; tokens only; loading/error states | UI | design/screens/worker/06-job-flow.html | 1 | Not started |  | Not requested
444 |  |  |  | P5 Booking & job | Y | App-Worker | worker/06-job-flow.html | Screen W-06g — Check-in · GPS ok · Bengali | Matches frame; tokens only; loading/error states | UI | design/screens/worker/06-job-flow.html | 1 | Not started |  | Not requested
445 |  |  |  | P5 Booking & job | Y | App-Worker | worker/06-job-flow.html | Screen W-06h — Check-in · too far → check in anyway | Matches frame; tokens only; loading/error states | UI | design/screens/worker/06-job-flow.html | 1 | Not started |  | Not requested
446 |  |  |  | P5 Booking & job | Y | App-Worker | worker/06-job-flow.html | Screen W-06i — Enter start code · Bengali | Matches frame; tokens only; loading/error states | UI | design/screens/worker/06-job-flow.html | 1 | Not started |  | Not requested
447 |  |  |  | P5 Booking & job | Y | App-Worker | worker/06-job-flow.html | Screen W-06j — Start code · locked | Matches frame; tokens only; loading/error states | UI | design/screens/worker/06-job-flow.html | 1 | Not started |  | Not requested
448 |  |  |  | P5 Booking & job | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
449 |  |  |  | P5 Booking & job | Y | App-Worker | worker/06-job-flow.html | Screen W-06k — Working · Bengali | Matches frame; tokens only; loading/error states | UI | design/screens/worker/06-job-flow.html | 1 | Not started |  | Not requested
450 |  |  |  | P5 Booking & job | Y | App-Worker | worker/06-job-flow.html | Screen W-06l — Check-out sheet | Matches frame; tokens only; loading/error states | UI | design/screens/worker/06-job-flow.html | 1 | Not started |  | Not requested
451 |  |  |  | P5 Booking & job | Y | App-Worker | worker/06-job-flow.html | Screen W-06m — Add days / move a day | Matches frame; tokens only; loading/error states | UI | design/screens/worker/06-job-flow.html | 1 | Not started |  | Not requested
452 |  |  |  | P5 Booking & job | Y | App-Worker | worker/06-job-flow.html | Screen W-06n — Can't complete the job | Matches frame; tokens only; loading/error states | UI | design/screens/worker/06-job-flow.html | 1 | Not started |  | Not requested
453 |  |  |  | P5 Booking & job | Y | App-Worker | worker/06-job-flow.html | Screen W-06o — Customer not home (after 30 min) | Matches frame; tokens only; loading/error states | UI | design/screens/worker/06-job-flow.html | 1 | Not started |  | Not requested
454 |  |  |  | P5 Booking & job | Y | App-Worker | worker/06-job-flow.html | Screen W-06p — Cancel booking · strike warning | Matches frame; tokens only; loading/error states | UI | design/screens/worker/06-job-flow.html | 1 | Not started |  | Not requested
455 |  |  |  | P5 Booking & job | Y | App-Worker | worker/06-job-flow.html | Screen W-06q — Active job · offline | Matches frame; tokens only; loading/error states | UI | design/screens/worker/06-job-flow.html | 1 | Not started |  | Not requested
456 |  |  |  | P5 Booking & job | Y | App-Worker | worker/06-job-flow.html | Screen W-06r — Customer asked to move a day | Matches frame; tokens only; loading/error states | UI | design/screens/worker/06-job-flow.html | 1 | Not started |  | Not requested
457 |  |  |  | P5 Booking & job | Y | App-Worker | worker/06-job-flow.html | Screen W-06s — Busy at that time (WORKER_BUSY_AT_TIME) | Matches frame; tokens only; loading/error states | UI | design/screens/worker/06-job-flow.html | 1 | Not started |  | Not requested
458 |  |  |  | P5 Booking & job | Y | App-Worker | worker/06-job-flow.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/worker/06-job-flow.html | 1 | Not started |  | Not requested
459 |  |  |  | P5 Booking & job | Y | App-Worker | worker/06-job-flow.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/worker/06-job-flow.html | 1 | Not started |  | Not requested
460 |  |  |  | P5 Booking & job | Y | Review | worker/06-job-flow.html | Review with Claude: worker/06-job-flow.html | All review comments fixed | Code review | design/screens/worker/06-job-flow.html | 1 | Not started |  | Not requested
461 |  |  |  | P5 Booking & job | Y | App-Customer | customer/10-booking-exceptions.html | Screen C-10a — Worker cancelled → finding someone else | Matches frame; tokens only; loading/error states | UI | design/screens/customer/10-booking-exceptions.html | 1 | Not started |  | Not requested
462 |  |  |  | P5 Booking & job | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
463 |  |  |  | P5 Booking & job | Y | App-Customer | customer/10-booking-exceptions.html | Screen C-10b — New shortlist after re-matching | Matches frame; tokens only; loading/error states | UI | design/screens/customer/10-booking-exceptions.html | 1 | Not started |  | Not requested
464 |  |  |  | P5 Booking & job | Y | App-Customer | customer/10-booking-exceptions.html | Screen C-10c — Job couldn't be finished | Matches frame; tokens only; loading/error states | UI | design/screens/customer/10-booking-exceptions.html | 1 | Not started |  | Not requested
465 |  |  |  | P5 Booking & job | Y | App-Customer | customer/10-booking-exceptions.html | Screen C-10d — You weren't home (missed visit) | Matches frame; tokens only; loading/error states | UI | design/screens/customer/10-booking-exceptions.html | 1 | Not started |  | Not requested
466 |  |  |  | P5 Booking & job | Y | App-Customer | customer/10-booking-exceptions.html | Screen C-10e — Book again · prefilled request | Matches frame; tokens only; loading/error states | UI | design/screens/customer/10-booking-exceptions.html | 1 | Not started |  | Not requested
467 |  |  |  | P5 Booking & job | Y | App-Customer | customer/10-booking-exceptions.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/customer/10-booking-exceptions.html | 1 | Not started |  | Not requested
468 |  |  |  | P5 Booking & job | Y | App-Customer | customer/10-booking-exceptions.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/customer/10-booking-exceptions.html | 1 | Not started |  | Not requested
469 |  |  |  | P5 Booking & job | Y | Review | customer/10-booking-exceptions.html | Review with Claude: customer/10-booking-exceptions.html | All review comments fixed | Code review | design/screens/customer/10-booking-exceptions.html | 1 | Not started |  | Not requested
470 |  |  |  | P5 Booking & job | Y | Review | milestone | Milestone demo: Worker goes on the way, checks in, start code, checks out; customer confirms; cancellations work | Demo recorded; README updated | Demo | plan/ | 1 | Not started |  | Not requested
471 |  |  |  | P6 Cash, earnings, reviews | Y | Learning | LLD-010 | Read LLD-010: Cash Payment, Ledger and Worker Earnings; list questions | Can explain the flow and tables | Domain | lld/lld-010-cash-payment-ledger-earnings.md | 1 | Not started |  | Not requested
472 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-010 | Flyway migration (1/4): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-010-cash-payment-ledger-earnings.md §3 | 1 | Not started |  | Not requested
473 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-010 | Flyway migration (2/4): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-010-cash-payment-ledger-earnings.md §3 | 1 | Not started |  | Not requested
474 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-010 | Flyway migration (3/4): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-010-cash-payment-ledger-earnings.md §3 | 1 | Not started |  | Not requested
475 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-010 | Flyway migration (4/4): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-010-cash-payment-ledger-earnings.md §3 | 1 | Not started |  | Not requested
476 |  |  |  | P6 Cash, earnings, reviews | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
477 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-010 | Entities + repositories (1/4) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-010-cash-payment-ledger-earnings.md §3 | 1 | Not started |  | Not requested
478 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-010 | Entities + repositories (2/4) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-010-cash-payment-ledger-earnings.md §3 | 1 | Not started |  | Not requested
479 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-010 | Entities + repositories (3/4) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-010-cash-payment-ledger-earnings.md §3 | 1 | Not started |  | Not requested
480 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-010 | Entities + repositories (4/4) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-010-cash-payment-ledger-earnings.md §3 | 1 | Not started |  | Not requested
481 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-010 | Ledger accounts + double-entry posting (sum = 0) | Unit tests cover happy + failure paths | Domain logic | lld/lld-010-cash-payment-ledger-earnings.md §2/§5/§6 | 1 | Not started |  | Not requested
482 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-010 | Cash payment: worker marks, customer confirms | Unit tests cover happy + failure paths | Domain logic | lld/lld-010-cash-payment-ledger-earnings.md §2/§5/§6 | 1 | Not started |  | Not requested
483 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-010 | Platform fee + worker earnings postings | Unit tests cover happy + failure paths | Domain logic | lld/lld-010-cash-payment-ledger-earnings.md §2/§5/§6 | 1 | Not started |  | Not requested
484 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-010 | Advance application against the bill | Unit tests cover happy + failure paths | Domain logic | lld/lld-010-cash-payment-ledger-earnings.md §2/§5/§6 | 1 | Not started |  | Not requested
485 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-010 | Dues balance + dues limit blocks new offers | Unit tests cover happy + failure paths | Domain logic | lld/lld-010-cash-payment-ledger-earnings.md §2/§5/§6 | 1 | Not started |  | Not requested
486 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-010 | Earnings summary query (day/week/month) | Unit tests cover happy + failure paths | Domain logic | lld/lld-010-cash-payment-ledger-earnings.md §2/§5/§6 | 1 | Not started |  | Not requested
487 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-010 | API POST /api/v1/jobs/{id}/payments/cash | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-010-cash-payment-ledger-earnings.md §4 | 1 | Not started |  | Not requested
488 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-010 | API POST /api/v1/payments/{id}/confirm-cash | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-010-cash-payment-ledger-earnings.md §4 | 1 | Not started |  | Not requested
489 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-010 | API GET /api/v1/jobs/{id}/payments | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-010-cash-payment-ledger-earnings.md §4 | 1 | Not started |  | Not requested
490 |  |  |  | P6 Cash, earnings, reviews | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
491 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-010 | API GET /api/v1/worker/earnings/summary | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-010-cash-payment-ledger-earnings.md §4 | 1 | Not started |  | Not requested
492 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-010 | API GET /api/v1/worker/earnings | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-010-cash-payment-ledger-earnings.md §4 | 1 | Not started |  | Not requested
493 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-010 | API POST /api/v1/admin/ledger/adjustments | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-010-cash-payment-ledger-earnings.md §4 | 1 | Not started |  | Not requested
494 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-010 | API GET /api/v1/admin/ledger/accounts/{type} | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-010-cash-payment-ledger-earnings.md §4 | 1 | Not started |  | Not requested
495 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-010 | API POST /api/v1/disputes | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-010-cash-payment-ledger-earnings.md §4 | 1 | Not started |  | Not requested
496 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-010 | Events: publish/consume via outbox; check error handling §7 | Outbox rows written; consumer idempotent | Events | lld/lld-010-cash-payment-ledger-earnings.md §7 | 1 | Not started |  | Not requested
497 |  |  |  | P6 Cash, earnings, reviews | Y | Review | LLD-010 | Module review with Claude: LLD-010 full diff + test plan §10 | All review comments fixed | Code review | lld/lld-010-cash-payment-ledger-earnings.md §10 | 1 | Not started |  | Not requested
498 |  |  |  | P6 Cash, earnings, reviews | Y | Learning | LLD-012 | Read LLD-012: Reviews, Ratings and Reputation Snapshot; list questions | Can explain the flow and tables | Domain | lld/lld-012-reviews-ratings.md | 1 | Not started |  | Not requested
499 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-012 | Flyway migration (1/2): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-012-reviews-ratings.md §3 | 1 | Not started |  | Not requested
500 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-012 | Flyway migration (2/2): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-012-reviews-ratings.md §3 | 1 | Not started |  | Not requested
501 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-012 | Entities + repositories (1/2) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-012-reviews-ratings.md §3 | 1 | Not started |  | Not requested
502 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-012 | Entities + repositories (2/2) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-012-reviews-ratings.md §3 | 1 | Not started |  | Not requested
503 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-012 | Review window + one review per side | Unit tests cover happy + failure paths | Domain logic | lld/lld-012-reviews-ratings.md §2/§5/§6 | 1 | Not started |  | Not requested
504 |  |  |  | P6 Cash, earnings, reviews | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
505 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-012 | Double-blind reveal rule | Unit tests cover happy + failure paths | Domain logic | lld/lld-012-reviews-ratings.md §2/§5/§6 | 1 | Not started |  | Not requested
506 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-012 | Reputation snapshot update via outbox event | Unit tests cover happy + failure paths | Domain logic | lld/lld-012-reviews-ratings.md §2/§5/§6 | 1 | Not started |  | Not requested
507 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-012 | API POST /api/v1/jobs/{jobId}/reviews | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-012-reviews-ratings.md §4 | 1 | Not started |  | Not requested
508 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-012 | API PUT /api/v1/reviews/{id} | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-012-reviews-ratings.md §4 | 1 | Not started |  | Not requested
509 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-012 | API GET /api/v1/jobs/{jobId}/reviews | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-012-reviews-ratings.md §4 | 1 | Not started |  | Not requested
510 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-012 | API POST /api/v1/reviews/{id}/reply | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-012-reviews-ratings.md §4 | 1 | Not started |  | Not requested
511 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-012 | API POST /api/v1/reviews/{id}/report | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-012-reviews-ratings.md §4 | 1 | Not started |  | Not requested
512 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-012 | API GET /api/v1/workers/{workerId}/reviews | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-012-reviews-ratings.md §4 | 1 | Not started |  | Not requested
513 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-012 | API GET /api/v1/workers/me/reputation | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-012-reviews-ratings.md §4 | 1 | Not started |  | Not requested
514 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-012 | API GET /api/v1/admin/reviews | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-012-reviews-ratings.md §4 | 1 | Not started |  | Not requested
515 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-012 | API POST /api/v1/admin/reviews/{id}/approve | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-012-reviews-ratings.md §4 | 1 | Not started |  | Not requested
516 |  |  |  | P6 Cash, earnings, reviews | Y | Backend | LLD-012 | Events: publish/consume via outbox; check error handling §7 | Outbox rows written; consumer idempotent | Events | lld/lld-012-reviews-ratings.md §7 | 1 | Not started |  | Not requested
517 |  |  |  | P6 Cash, earnings, reviews | Y | Review | LLD-012 | Module review with Claude: LLD-012 full diff + test plan §10 | All review comments fixed | Code review | lld/lld-012-reviews-ratings.md §10 | 1 | Not started |  | Not requested
518 |  |  |  | P6 Cash, earnings, reviews | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
519 |  |  |  | P6 Cash, earnings, reviews | Y | App-Customer | customer/08-payment.html | Screen C-08a — Bill & pay | Matches frame; tokens only; loading/error states | UI | design/screens/customer/08-payment.html | 1 | Not started |  | Not requested
520 |  |  |  | P6 Cash, earnings, reviews | Y | App-Customer | customer/08-payment.html | Screen C-08b — Provider checkout hand-off | Matches frame; tokens only; loading/error states | UI | design/screens/customer/08-payment.html | 1 | Not started |  | Not requested
521 |  |  |  | P6 Cash, earnings, reviews | Y | App-Customer | customer/08-payment.html | Screen C-08c — Payment pending | Matches frame; tokens only; loading/error states | UI | design/screens/customer/08-payment.html | 1 | Not started |  | Not requested
522 |  |  |  | P6 Cash, earnings, reviews | Y | App-Customer | customer/08-payment.html | Screen C-08d — Payment failed | Matches frame; tokens only; loading/error states | UI | design/screens/customer/08-payment.html | 1 | Not started |  | Not requested
523 |  |  |  | P6 Cash, earnings, reviews | Y | App-Customer | customer/08-payment.html | Screen C-08e — Cash — confirm you paid | Matches frame; tokens only; loading/error states | UI | design/screens/customer/08-payment.html | 1 | Not started |  | Not requested
524 |  |  |  | P6 Cash, earnings, reviews | Y | App-Customer | customer/08-payment.html | Screen C-08f — Payment success | Matches frame; tokens only; loading/error states | UI | design/screens/customer/08-payment.html | 1 | Not started |  | Not requested
525 |  |  |  | P6 Cash, earnings, reviews | Y | App-Customer | customer/08-payment.html | Screen C-08g — Receipt (in app) | Matches frame; tokens only; loading/error states | UI | design/screens/customer/08-payment.html | 1 | Not started |  | Not requested
526 |  |  |  | P6 Cash, earnings, reviews | Y | App-Customer | customer/08-payment.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/customer/08-payment.html | 1 | Not started |  | Not requested
527 |  |  |  | P6 Cash, earnings, reviews | Y | App-Customer | customer/08-payment.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/customer/08-payment.html | 1 | Not started |  | Not requested
528 |  |  |  | P6 Cash, earnings, reviews | Y | Review | customer/08-payment.html | Review with Claude: customer/08-payment.html | All review comments fixed | Code review | design/screens/customer/08-payment.html | 1 | Not started |  | Not requested
529 |  |  |  | P6 Cash, earnings, reviews | Y | App-Worker | worker/08-earnings.html | Screen W-08a — Earnings | Matches frame; tokens only; loading/error states | UI | design/screens/worker/08-earnings.html | 1 | Not started |  | Not requested
530 |  |  |  | P6 Cash, earnings, reviews | Y | App-Worker | worker/08-earnings.html | Screen W-08b — Earnings · dues over limit | Matches frame; tokens only; loading/error states | UI | design/screens/worker/08-earnings.html | 1 | Not started |  | Not requested
531 |  |  |  | P6 Cash, earnings, reviews | Y | App-Worker | worker/08-earnings.html | Screen W-08c — Pay dues by UPI · provider checkout | Matches frame; tokens only; loading/error states | UI | design/screens/worker/08-earnings.html | 1 | Not started |  | Not requested
532 |  |  |  | P6 Cash, earnings, reviews | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
533 |  |  |  | P6 Cash, earnings, reviews | Y | App-Worker | worker/08-earnings.html | Screen W-08d — Dues paid | Matches frame; tokens only; loading/error states | UI | design/screens/worker/08-earnings.html | 1 | Not started |  | Not requested
534 |  |  |  | P6 Cash, earnings, reviews | Y | App-Worker | worker/08-earnings.html | Screen W-08e — Payouts to bank | Matches frame; tokens only; loading/error states | UI | design/screens/worker/08-earnings.html | 1 | Not started |  | Not requested
535 |  |  |  | P6 Cash, earnings, reviews | Y | App-Worker | worker/08-earnings.html | Screen W-08f — My reviews | Matches frame; tokens only; loading/error states | UI | design/screens/worker/08-earnings.html | 1 | Not started |  | Not requested
536 |  |  |  | P6 Cash, earnings, reviews | Y | App-Worker | worker/08-earnings.html | Screen W-08g — Reply to a review | Matches frame; tokens only; loading/error states | UI | design/screens/worker/08-earnings.html | 1 | Not started |  | Not requested
537 |  |  |  | P6 Cash, earnings, reviews | Y | App-Worker | worker/08-earnings.html | Screen W-08h — Complaint · answer within 48 h | Matches frame; tokens only; loading/error states | UI | design/screens/worker/08-earnings.html | 1 | Not started |  | Not requested
538 |  |  |  | P6 Cash, earnings, reviews | Y | App-Worker | worker/08-earnings.html | Screen W-08i — Complaint · decision | Matches frame; tokens only; loading/error states | UI | design/screens/worker/08-earnings.html | 1 | Not started |  | Not requested
539 |  |  |  | P6 Cash, earnings, reviews | Y | App-Worker | worker/08-earnings.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/worker/08-earnings.html | 1 | Not started |  | Not requested
540 |  |  |  | P6 Cash, earnings, reviews | Y | App-Worker | worker/08-earnings.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/worker/08-earnings.html | 1 | Not started |  | Not requested
541 |  |  |  | P6 Cash, earnings, reviews | Y | Review | worker/08-earnings.html | Review with Claude: worker/08-earnings.html | All review comments fixed | Code review | design/screens/worker/08-earnings.html | 1 | Not started |  | Not requested
542 |  |  |  | P6 Cash, earnings, reviews | Y | App-Customer | customer/09-reviews.html | Screen C-09a — Rate worker | Matches frame; tokens only; loading/error states | UI | design/screens/customer/09-reviews.html | 1 | Not started |  | Not requested
543 |  |  |  | P6 Cash, earnings, reviews | Y | App-Customer | customer/09-reviews.html | Screen C-09b — Review submitted | Matches frame; tokens only; loading/error states | UI | design/screens/customer/09-reviews.html | 1 | Not started |  | Not requested
544 |  |  |  | P6 Cash, earnings, reviews | Y | App-Customer | customer/09-reviews.html | Screen C-09c — My reviews | Matches frame; tokens only; loading/error states | UI | design/screens/customer/09-reviews.html | 1 | Not started |  | Not requested
545 |  |  |  | P6 Cash, earnings, reviews | Y | App-Customer | customer/09-reviews.html | Screen C-09d — Edit review | Matches frame; tokens only; loading/error states | UI | design/screens/customer/09-reviews.html | 1 | Not started |  | Not requested
546 |  |  |  | P6 Cash, earnings, reviews | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
547 |  |  |  | P6 Cash, earnings, reviews | Y | App-Customer | customer/09-reviews.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/customer/09-reviews.html | 1 | Not started |  | Not requested
548 |  |  |  | P6 Cash, earnings, reviews | Y | App-Customer | customer/09-reviews.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/customer/09-reviews.html | 1 | Not started |  | Not requested
549 |  |  |  | P6 Cash, earnings, reviews | Y | Review | customer/09-reviews.html | Review with Claude: customer/09-reviews.html | All review comments fixed | Code review | design/screens/customer/09-reviews.html | 1 | Not started |  | Not requested
550 |  |  |  | P6 Cash, earnings, reviews | Y | Review | milestone | Milestone demo: Job paid in cash, ledger balanced, worker sees earnings + dues, both sides review | Demo recorded; README updated | Demo | plan/ | 1 | Not started |  | Not requested
551 |  |  |  | P7 Notifications & account | Y | Learning | LLD-013 | Read LLD-013: Notifications — Push, Email, In-app Inbox via Outbox; list questions | Can explain the flow and tables | Domain | lld/lld-013-notifications.md | 1 | Not started |  | Not requested
552 |  |  |  | P7 Notifications & account | Y | Backend | LLD-013 | Flyway migration: tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-013-notifications.md §3 | 1 | Not started |  | Not requested
553 |  |  |  | P7 Notifications & account | Y | Backend | LLD-013 | Entities + repositories + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-013-notifications.md §3 | 1 | Not started |  | Not requested
554 |  |  |  | P7 Notifications & account | Y | Backend | LLD-013 | Notification templates per locale | Unit tests cover happy + failure paths | Domain logic | lld/lld-013-notifications.md §2/§5/§6 | 1 | Not started |  | Not requested
555 |  |  |  | P7 Notifications & account | Y | Backend | LLD-013 | Outbox consumer → channel router (push/email/inbox) | Unit tests cover happy + failure paths | Domain logic | lld/lld-013-notifications.md §2/§5/§6 | 1 | Not started |  | Not requested
556 |  |  |  | P7 Notifications & account | Y | Backend | LLD-013 | FCM push sender + device tokens | Unit tests cover happy + failure paths | Domain logic | lld/lld-013-notifications.md §2/§5/§6 | 1 | Not started |  | Not requested
557 |  |  |  | P7 Notifications & account | Y | Backend | LLD-013 | Preferences + quiet hours | Unit tests cover happy + failure paths | Domain logic | lld/lld-013-notifications.md §2/§5/§6 | 1 | Not started |  | Not requested
558 |  |  |  | P7 Notifications & account | Y | Backend | LLD-013 | In-app inbox cursor pagination | Unit tests cover happy + failure paths | Domain logic | lld/lld-013-notifications.md §2/§5/§6 | 1 | Not started |  | Not requested
559 |  |  |  | P7 Notifications & account | Y | Backend | LLD-013 | API GET /api/v1/notifications | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-013-notifications.md §4 | 1 | Not started |  | Not requested
560 |  |  |  | P7 Notifications & account | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
561 |  |  |  | P7 Notifications & account | Y | Backend | LLD-013 | API GET /api/v1/notifications/unread-count | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-013-notifications.md §4 | 1 | Not started |  | Not requested
562 |  |  |  | P7 Notifications & account | Y | Backend | LLD-013 | API POST /api/v1/notifications/{id}/read | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-013-notifications.md §4 | 1 | Not started |  | Not requested
563 |  |  |  | P7 Notifications & account | Y | Backend | LLD-013 | API POST /api/v1/notifications/read-all | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-013-notifications.md §4 | 1 | Not started |  | Not requested
564 |  |  |  | P7 Notifications & account | Y | Backend | LLD-013 | API PUT /api/v1/me/devices/current/push-token | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-013-notifications.md §4 | 1 | Not started |  | Not requested
565 |  |  |  | P7 Notifications & account | Y | Backend | LLD-013 | API DELETE /api/v1/me/devices/current/push-token | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-013-notifications.md §4 | 1 | Not started |  | Not requested
566 |  |  |  | P7 Notifications & account | Y | Backend | LLD-013 | API GET /api/v1/me/notification-preferences | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-013-notifications.md §4 | 1 | Not started |  | Not requested
567 |  |  |  | P7 Notifications & account | Y | Backend | LLD-013 | API GET /api/v1/admin/notifications | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-013-notifications.md §4 | 1 | Not started |  | Not requested
568 |  |  |  | P7 Notifications & account | Y | Backend | LLD-013 | API POST /api/v1/admin/notifications/{id}/retry | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-013-notifications.md §4 | 1 | Not started |  | Not requested
569 |  |  |  | P7 Notifications & account | Y | Backend | LLD-013 | Events: publish/consume via outbox; check error handling §7 | Outbox rows written; consumer idempotent | Events | lld/lld-013-notifications.md §7 | 1 | Not started |  | Not requested
570 |  |  |  | P7 Notifications & account | Y | Review | LLD-013 | Module review with Claude: LLD-013 full diff + test plan §10 | All review comments fixed | Code review | lld/lld-013-notifications.md §10 | 1 | Not started |  | Not requested
571 |  |  |  | P7 Notifications & account | Y | Learning | — | expo-notifications + FCM setup; receive a test push | Notes in learning log; small sample committed | Push |  | 1 | Not started |  | Not requested
572 |  |  |  | P7 Notifications & account | Y | App-Worker | worker/09-account-support.html | Screen W-09a — Notifications inbox · Bengali | Matches frame; tokens only; loading/error states | UI | design/screens/worker/09-account-support.html | 1 | Not started |  | Not requested
573 |  |  |  | P7 Notifications & account | Y | App-Worker | worker/09-account-support.html | Screen W-09b — Notification settings | Matches frame; tokens only; loading/error states | UI | design/screens/worker/09-account-support.html | 1 | Not started |  | Not requested
574 |  |  |  | P7 Notifications & account | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
575 |  |  |  | P7 Notifications & account | Y | App-Worker | worker/09-account-support.html | Screen W-09c — Help & support | Matches frame; tokens only; loading/error states | UI | design/screens/worker/09-account-support.html | 1 | Not started |  | Not requested
576 |  |  |  | P7 Notifications & account | Y | App-Worker | worker/09-account-support.html | Screen W-09d — Report a problem · 1 What | Matches frame; tokens only; loading/error states | UI | design/screens/worker/09-account-support.html | 1 | Not started |  | Not requested
577 |  |  |  | P7 Notifications & account | Y | App-Worker | worker/09-account-support.html | Screen W-09e — Report a problem · 2 Details + photos | Matches frame; tokens only; loading/error states | UI | design/screens/worker/09-account-support.html | 1 | Not started |  | Not requested
578 |  |  |  | P7 Notifications & account | Y | App-Worker | worker/09-account-support.html | Screen W-09f — Report sent · customer has 48 h | Matches frame; tokens only; loading/error states | UI | design/screens/worker/09-account-support.html | 1 | Not started |  | Not requested
579 |  |  |  | P7 Notifications & account | Y | App-Worker | worker/09-account-support.html | Screen W-09g — Account paused · can log in | Matches frame; tokens only; loading/error states | UI | design/screens/worker/09-account-support.html | 1 | Not started |  | Not requested
580 |  |  |  | P7 Notifications & account | Y | App-Worker | worker/09-account-support.html | Screen W-09h — Can't log in (blockLogin) | Matches frame; tokens only; loading/error states | UI | design/screens/worker/09-account-support.html | 1 | Not started |  | Not requested
581 |  |  |  | P7 Notifications & account | Y | App-Worker | worker/09-account-support.html | Screen W-09i — Forgot password | Matches frame; tokens only; loading/error states | UI | design/screens/worker/09-account-support.html | 1 | Not started |  | Not requested
582 |  |  |  | P7 Notifications & account | Y | App-Worker | worker/09-account-support.html | Screen W-09j — Reset password | Matches frame; tokens only; loading/error states | UI | design/screens/worker/09-account-support.html | 1 | Not started |  | Not requested
583 |  |  |  | P7 Notifications & account | Y | App-Worker | worker/09-account-support.html | Screen W-09k — Logged out on this phone · Bengali | Matches frame; tokens only; loading/error states | UI | design/screens/worker/09-account-support.html | 1 | Not started |  | Not requested
584 |  |  |  | P7 Notifications & account | Y | App-Worker | worker/09-account-support.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/worker/09-account-support.html | 1 | Not started |  | Not requested
585 |  |  |  | P7 Notifications & account | Y | App-Worker | worker/09-account-support.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/worker/09-account-support.html | 1 | Not started |  | Not requested
586 |  |  |  | P7 Notifications & account | Y | Review | worker/09-account-support.html | Review with Claude: worker/09-account-support.html | All review comments fixed | Code review | design/screens/worker/09-account-support.html | 1 | Not started |  | Not requested
587 |  |  |  | P7 Notifications & account | Y | App-Customer | customer/11-account.html | Screen C-11a — Account | Matches frame; tokens only; loading/error states | UI | design/screens/customer/11-account.html | 1 | Not started |  | Not requested
588 |  |  |  | P7 Notifications & account | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
589 |  |  |  | P7 Notifications & account | Y | App-Customer | customer/11-account.html | Screen C-11b — Edit profile | Matches frame; tokens only; loading/error states | UI | design/screens/customer/11-account.html | 1 | Not started |  | Not requested
590 |  |  |  | P7 Notifications & account | Y | App-Customer | customer/11-account.html | Screen C-11c — Language | Matches frame; tokens only; loading/error states | UI | design/screens/customer/11-account.html | 1 | Not started |  | Not requested
591 |  |  |  | P7 Notifications & account | Y | App-Customer | customer/11-account.html | Screen C-11d — Notification settings | Matches frame; tokens only; loading/error states | UI | design/screens/customer/11-account.html | 1 | Not started |  | Not requested
592 |  |  |  | P7 Notifications & account | Y | App-Customer | customer/11-account.html | Screen C-11e — Notifications inbox | Matches frame; tokens only; loading/error states | UI | design/screens/customer/11-account.html | 1 | Not started |  | Not requested
593 |  |  |  | P7 Notifications & account | Y | App-Customer | customer/11-account.html | Screen C-11f — Privacy & security | Matches frame; tokens only; loading/error states | UI | design/screens/customer/11-account.html | 1 | Not started |  | Not requested
594 |  |  |  | P7 Notifications & account | Y | App-Customer | customer/11-account.html | Screen C-11g — Your consents | Matches frame; tokens only; loading/error states | UI | design/screens/customer/11-account.html | 1 | Not started |  | Not requested
595 |  |  |  | P7 Notifications & account | Y | App-Customer | customer/11-account.html | Screen C-11h — Change password | Matches frame; tokens only; loading/error states | UI | design/screens/customer/11-account.html | 1 | Not started |  | Not requested
596 |  |  |  | P7 Notifications & account | Y | App-Customer | customer/11-account.html | Screen C-11i — Your data summary | Matches frame; tokens only; loading/error states | UI | design/screens/customer/11-account.html | 1 | Not started |  | Not requested
597 |  |  |  | P7 Notifications & account | Y | App-Customer | customer/11-account.html | Screen C-11j — Delete account · blocked | Matches frame; tokens only; loading/error states | UI | design/screens/customer/11-account.html | 1 | Not started |  | Not requested
598 |  |  |  | P7 Notifications & account | Y | App-Customer | customer/11-account.html | Screen C-11k — Delete account · confirm | Matches frame; tokens only; loading/error states | UI | design/screens/customer/11-account.html | 1 | Not started |  | Not requested
599 |  |  |  | P7 Notifications & account | Y | App-Customer | customer/11-account.html | Screen C-11l — Terms & policies | Matches frame; tokens only; loading/error states | UI | design/screens/customer/11-account.html | 1 | Not started |  | Not requested
600 |  |  |  | P7 Notifications & account | Y | App-Customer | customer/11-account.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/customer/11-account.html | 1 | Not started |  | Not requested
601 |  |  |  | P7 Notifications & account | Y | App-Customer | customer/11-account.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/customer/11-account.html | 1 | Not started |  | Not requested
602 |  |  |  | P7 Notifications & account | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
603 |  |  |  | P7 Notifications & account | Y | Review | customer/11-account.html | Review with Claude: customer/11-account.html | All review comments fixed | Code review | design/screens/customer/11-account.html | 1 | Not started |  | Not requested
604 |  |  |  | P7 Notifications & account | Y | Review | milestone | Milestone demo: Push + email + inbox for key events; account, privacy and settings screens done | Demo recorded; README updated | Demo | plan/ | 1 | Not started |  | Not requested
605 |  |  |  | P8 Verification & admin console | Y | Learning | LLD-016 | Read LLD-016: Worker Verification — Identity, Trade, Police Verification, Expiry; list questions | Can explain the flow and tables | Domain | lld/lld-016-worker-verification.md | 1 | Not started |  | Not requested
606 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-016 | Flyway migration (1/2): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-016-worker-verification.md §3 | 1 | Not started |  | Not requested
607 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-016 | Flyway migration (2/2): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-016-worker-verification.md §3 | 1 | Not started |  | Not requested
608 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-016 | Entities + repositories (1/2) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-016-worker-verification.md §3 | 1 | Not started |  | Not requested
609 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-016 | Entities + repositories (2/2) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-016-worker-verification.md §3 | 1 | Not started |  | Not requested
610 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-016 | Document state machine: PENDING → APPROVED/REJECTED/EXPIRED | Unit tests cover happy + failure paths | Domain logic | lld/lld-016-worker-verification.md §2/§5/§6 | 1 | Not started |  | Not requested
611 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-016 | Encrypt PAN at rest + masking | Unit tests cover happy + failure paths | Domain logic | lld/lld-016-worker-verification.md §2/§5/§6 | 1 | Not started |  | Not requested
612 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-016 | Expiry job + revocation effects on ACTIVE | Unit tests cover happy + failure paths | Domain logic | lld/lld-016-worker-verification.md §2/§5/§6 | 1 | Not started |  | Not requested
613 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-016 | API GET /api/v1/workers/me/verifications | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-016-worker-verification.md §4 | 1 | Not started |  | Not requested
614 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-016 | API POST /api/v1/workers/me/verifications | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-016-worker-verification.md §4 | 1 | Not started |  | Not requested
615 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-016 | API GET /api/v1/admin/verifications | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-016-worker-verification.md §4 | 1 | Not started |  | Not requested
616 |  |  |  | P8 Verification & admin console | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
617 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-016 | API POST /api/v1/admin/verifications/{id}/claim | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-016-worker-verification.md §4 | 1 | Not started |  | Not requested
618 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-016 | API GET /api/v1/admin/verifications/{id} | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-016-worker-verification.md §4 | 1 | Not started |  | Not requested
619 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-016 | API POST /api/v1/admin/verifications/{id}/documents/{documentId}/view-url | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-016-worker-verification.md §4 | 1 | Not started |  | Not requested
620 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-016 | API POST /api/v1/admin/verifications/{id}/approve | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-016-worker-verification.md §4 | 1 | Not started |  | Not requested
621 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-016 | API POST /api/v1/admin/verifications/{id}/reject | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-016-worker-verification.md §4 | 1 | Not started |  | Not requested
622 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-016 | API POST /api/v1/admin/verifications/{id}/revoke | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-016-worker-verification.md §4 | 1 | Not started |  | Not requested
623 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-016 | API POST /api/v1/admin/verifications/{id}/revoke/confirm | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-016-worker-verification.md §4 | 1 | Not started |  | Not requested
624 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-016 | Events: publish/consume via outbox; check error handling §7 | Outbox rows written; consumer idempotent | Events | lld/lld-016-worker-verification.md §7 | 1 | Not started |  | Not requested
625 |  |  |  | P8 Verification & admin console | Y | Review | LLD-016 | Module review with Claude: LLD-016 full diff + test plan §10 | All review comments fixed | Code review | lld/lld-016-worker-verification.md §10 | 1 | Not started |  | Not requested
626 |  |  |  | P8 Verification & admin console | Y | Learning | LLD-020 | Read LLD-020: Admin Staff, Permissions, Account Actions and Ops Queues; list questions | Can explain the flow and tables | Domain | lld/lld-020-admin-operations.md | 1 | Not started |  | Not requested
627 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | Flyway migration (1/4): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-020-admin-operations.md §3 | 1 | Not started |  | Not requested
628 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | Flyway migration (2/4): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-020-admin-operations.md §3 | 1 | Not started |  | Not requested
629 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | Flyway migration (3/4): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-020-admin-operations.md §3 | 1 | Not started |  | Not requested
630 |  |  |  | P8 Verification & admin console | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
631 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | Flyway migration (4/4): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-020-admin-operations.md §3 | 1 | Not started |  | Not requested
632 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | Entities + repositories (1/4) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-020-admin-operations.md §3 | 1 | Not started |  | Not requested
633 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | Entities + repositories (2/4) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-020-admin-operations.md §3 | 1 | Not started |  | Not requested
634 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | Entities + repositories (3/4) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-020-admin-operations.md §3 | 1 | Not started |  | Not requested
635 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | Entities + repositories (4/4) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-020-admin-operations.md §3 | 1 | Not started |  | Not requested
636 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | Staff accounts + roles/permissions matrix | Unit tests cover happy + failure paths | Domain logic | lld/lld-020-admin-operations.md §2/§5/§6 | 1 | Not started |  | Not requested
637 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | TOTP MFA enrol/verify + MFA window | Unit tests cover happy + failure paths | Domain logic | lld/lld-020-admin-operations.md §2/§5/§6 | 1 | Not started |  | Not requested
638 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | Audit log on every admin action | Unit tests cover happy + failure paths | Domain logic | lld/lld-020-admin-operations.md §2/§5/§6 | 1 | Not started |  | Not requested
639 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | PII reveal with reason | Unit tests cover happy + failure paths | Domain logic | lld/lld-020-admin-operations.md §2/§5/§6 | 1 | Not started |  | Not requested
640 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | Ops queues as queries over module ports | Unit tests cover happy + failure paths | Domain logic | lld/lld-020-admin-operations.md §2/§5/§6 | 1 | Not started |  | Not requested
641 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | Suspend user → cancel + re-match bookings | Unit tests cover happy + failure paths | Domain logic | lld/lld-020-admin-operations.md §2/§5/§6 | 1 | Not started |  | Not requested
642 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API GET /api/v1/admin/me | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
643 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API POST /api/v1/admin/me/mfa/enroll | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
644 |  |  |  | P8 Verification & admin console | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
645 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API POST /api/v1/admin/me/mfa/verify | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
646 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API GET /api/v1/admin/staff | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
647 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API POST /api/v1/admin/staff | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
648 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API POST /api/v1/admin/staff/{id}/grants | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
649 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API POST /api/v1/admin/staff/{id}/suspend | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
650 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API GET /api/v1/admin/users | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
651 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API GET /api/v1/admin/users/{userId} | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
652 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API POST /api/v1/admin/users/{userId}/reveal | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
653 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API POST /api/v1/admin/customers/{customerId}/suspend | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
654 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API POST /api/v1/admin/workers/{workerId}/suspend | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
655 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API POST /api/v1/admin/users/{userId}/restrictions | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
656 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API POST /api/v1/admin/restrictions/{id}/lift | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
657 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API GET /api/v1/admin/ops/queues | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
658 |  |  |  | P8 Verification & admin console | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
659 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API GET /api/v1/admin/ops/queues/{queue} | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
660 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API POST /api/v1/admin/ops/queues/{queue}/items/{itemId}/ack | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
661 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API POST /api/v1/admin/ops/outbox/{eventId}/retry | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
662 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API GET /api/v1/admin/audit-events | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
663 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API GET /api/v1/admin/workers/{id}/schedule | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
664 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API POST /api/v1/admin/customers/{id}/suspend | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
665 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API POST /api/v1/admin/workers/{id}/suspend | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
666 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API GET /api/v1/admin/ops/queues[/{queue}] | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
667 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API GET /api/v1/admin/ledger/accounts/{type} | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
668 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API GET /api/v1/admin/payments | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
669 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API GET /api/v1/admin/payouts | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
670 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API POST /api/v1/admin/ledger/adjustments | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
671 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API POST /api/v1/admin/payments/{id}/refunds | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
672 |  |  |  | P8 Verification & admin console | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
673 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API DELETE /api/v1/admin/workers/{id}/payout-hold | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
674 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API POST /api/v1/admin/payout-accounts/{id}/approve | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
675 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API GET /api/v1/admin/bookings[/{id}] | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
676 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API GET /api/v1/admin/jobs[/{id}] | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
677 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API POST /api/v1/admin/bookings/{id}/cancel | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
678 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API POST /api/v1/admin/workers/{id}/strikes | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
679 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API GET /api/v1/admin/disputes[/{id}] | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
680 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API POST /api/v1/admin/disputes | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
681 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API POST /api/v1/admin/disputes/{id}/resolve | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
682 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API GET /api/v1/admin/notifications | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
683 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | API POST /api/v1/admin/notifications/{id}/retry | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-020-admin-operations.md §4 | 1 | Not started |  | Not requested
684 |  |  |  | P8 Verification & admin console | Y | Backend | LLD-020 | Events: publish/consume via outbox; check error handling §7 | Outbox rows written; consumer idempotent | Events | lld/lld-020-admin-operations.md §7 | 1 | Not started |  | Not requested
685 |  |  |  | P8 Verification & admin console | Y | Review | LLD-020 | Module review with Claude: LLD-020 full diff + test plan §10 | All review comments fixed | Code review | lld/lld-020-admin-operations.md §10 | 1 | Not started |  | Not requested
686 |  |  |  | P8 Verification & admin console | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
687 |  |  |  | P8 Verification & admin console | Y | Learning | — | React + Vite + React Router for the admin web app | Notes in learning log; small sample committed | React web |  | 1 | Not started |  | Not requested
688 |  |  |  | P8 Verification & admin console | Y | Admin web | admin | Admin app shell: Vite + TS, layout with sidebar, API client reuse | Login page loads in browser | React web | design/screens/admin/01-access.html | 1 | Not started |  | Not requested
689 |  |  |  | P8 Verification & admin console | Y | Admin web | admin | Table component: sort, cursor paging, filters | Used by user lookup | Tables | design/screens/01-components.html | 1 | Not started |  | Not requested
690 |  |  |  | P8 Verification & admin console | Y | App-Worker | worker/03-verification.html | Screen W-03b — ID proof · choose document | Matches frame; tokens only; loading/error states | UI | design/screens/worker/03-verification.html | 1 | Not started |  | Not requested
691 |  |  |  | P8 Verification & admin console | Y | App-Worker | worker/03-verification.html | Screen W-03c — Capture front / back | Matches frame; tokens only; loading/error states | UI | design/screens/worker/03-verification.html | 1 | Not started |  | Not requested
692 |  |  |  | P8 Verification & admin console | Y | App-Worker | worker/03-verification.html | Screen W-03d — Selfie holding card | Matches frame; tokens only; loading/error states | UI | design/screens/worker/03-verification.html | 1 | Not started |  | Not requested
693 |  |  |  | P8 Verification & admin console | Y | App-Worker | worker/03-verification.html | Screen W-03e — Document number + check | Matches frame; tokens only; loading/error states | UI | design/screens/worker/03-verification.html | 1 | Not started |  | Not requested
694 |  |  |  | P8 Verification & admin console | Y | App-Worker | worker/03-verification.html | Screen W-03f — Police verification | Matches frame; tokens only; loading/error states | UI | design/screens/worker/03-verification.html | 1 | Not started |  | Not requested
695 |  |  |  | P8 Verification & admin console | Y | App-Worker | worker/03-verification.html | Screen W-03g — Electrical licence | Matches frame; tokens only; loading/error states | UI | design/screens/worker/03-verification.html | 1 | Not started |  | Not requested
696 |  |  |  | P8 Verification & admin console | Y | App-Worker | worker/03-verification.html | Screen W-03h — Submitted · in review | Matches frame; tokens only; loading/error states | UI | design/screens/worker/03-verification.html | 1 | Not started |  | Not requested
697 |  |  |  | P8 Verification & admin console | Y | App-Worker | worker/03-verification.html | Screen W-03i — Verified | Matches frame; tokens only; loading/error states | UI | design/screens/worker/03-verification.html | 1 | Not started |  | Not requested
698 |  |  |  | P8 Verification & admin console | Y | App-Worker | worker/03-verification.html | Screen W-03k — Expiring soon · renew | Matches frame; tokens only; loading/error states | UI | design/screens/worker/03-verification.html | 1 | Not started |  | Not requested
699 |  |  |  | P8 Verification & admin console | Y | App-Worker | worker/03-verification.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/worker/03-verification.html | 1 | Not started |  | Not requested
700 |  |  |  | P8 Verification & admin console | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
701 |  |  |  | P8 Verification & admin console | Y | App-Worker | worker/03-verification.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/worker/03-verification.html | 1 | Not started |  | Not requested
702 |  |  |  | P8 Verification & admin console | Y | Review | worker/03-verification.html | Review with Claude: worker/03-verification.html | All review comments fixed | Code review | design/screens/worker/03-verification.html | 1 | Not started |  | Not requested
703 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/01-access.html | Screen A-01a — Staff login | Matches frame; tokens only; loading/error states | UI | design/screens/admin/01-access.html | 1 | Not started |  | Not requested
704 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/01-access.html | Screen A-01b — Set up authenticator (MFA enrol) | Matches frame; tokens only; loading/error states | UI | design/screens/admin/01-access.html | 1 | Not started |  | Not requested
705 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/01-access.html | Screen A-01c — Enter authenticator code | Matches frame; tokens only; loading/error states | UI | design/screens/admin/01-access.html | 1 | Not started |  | Not requested
706 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/01-access.html | Screen A-01d — Too many wrong codes (MFA lockout) | Matches frame; tokens only; loading/error states | UI | design/screens/admin/01-access.html | 1 | Not started |  | Not requested
707 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/01-access.html | Screen A-01e — Ops dashboard · ops queues | Matches frame; tokens only; loading/error states | UI | design/screens/admin/01-access.html | 1 | Not started |  | Not requested
708 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/01-access.html | Screen A-01f — Queue · flagged check-ins + acknowledge | Matches frame; tokens only; loading/error states | UI | design/screens/admin/01-access.html | 1 | Not started |  | Not requested
709 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/01-access.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/admin/01-access.html | 1 | Not started |  | Not requested
710 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/01-access.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/admin/01-access.html | 1 | Not started |  | Not requested
711 |  |  |  | P8 Verification & admin console | Y | Review | admin/01-access.html | Review with Claude: admin/01-access.html | All review comments fixed | Code review | design/screens/admin/01-access.html | 1 | Not started |  | Not requested
712 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/02-people.html | Screen A-02a — User lookup (search-first) | Matches frame; tokens only; loading/error states | UI | design/screens/admin/02-people.html | 1 | Not started |  | Not requested
713 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/02-people.html | Screen A-02b — Customer detail | Matches frame; tokens only; loading/error states | UI | design/screens/admin/02-people.html | 1 | Not started |  | Not requested
714 |  |  |  | P8 Verification & admin console | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
715 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/02-people.html | Screen A-02c — Reveal contact details (PII reveal) | Matches frame; tokens only; loading/error states | UI | design/screens/admin/02-people.html | 1 | Not started |  | Not requested
716 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/02-people.html | Screen A-02d — Customer · suspend & add / lift restriction dialogs | Matches frame; tokens only; loading/error states | UI | design/screens/admin/02-people.html | 1 | Not started |  | Not requested
717 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/02-people.html | Screen A-02e — Worker detail | Matches frame; tokens only; loading/error states | UI | design/screens/admin/02-people.html | 1 | Not started |  | Not requested
718 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/02-people.html | Screen A-02f — Worker · suspend dialog (blockLogin + bookings to cancel) | Matches frame; tokens only; loading/error states | UI | design/screens/admin/02-people.html | 1 | Not started |  | Not requested
719 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/02-people.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/admin/02-people.html | 1 | Not started |  | Not requested
720 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/02-people.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/admin/02-people.html | 1 | Not started |  | Not requested
721 |  |  |  | P8 Verification & admin console | Y | Review | admin/02-people.html | Review with Claude: admin/02-people.html | All review comments fixed | Code review | design/screens/admin/02-people.html | 1 | Not started |  | Not requested
722 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/03-marketplace.html | Screen A-03a — Requests (read-only) | Matches frame; tokens only; loading/error states | UI | design/screens/admin/03-marketplace.html | 1 | Not started |  | Not requested
723 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/03-marketplace.html | Screen A-03b — Bookings | Matches frame; tokens only; loading/error states | UI | design/screens/admin/03-marketplace.html | 1 | Not started |  | Not requested
724 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/03-marketplace.html | Screen A-03c — Booking / job detail · fixed (was "Booking detail (2)") | Matches frame; tokens only; loading/error states | UI | design/screens/admin/03-marketplace.html | 1 | Not started |  | Not requested
725 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/03-marketplace.html | Screen A-03d — Admin cancel booking dialog | Matches frame; tokens only; loading/error states | UI | design/screens/admin/03-marketplace.html | 1 | Not started |  | Not requested
726 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/03-marketplace.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/admin/03-marketplace.html | 1 | Not started |  | Not requested
727 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/03-marketplace.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/admin/03-marketplace.html | 1 | Not started |  | Not requested
728 |  |  |  | P8 Verification & admin console | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
729 |  |  |  | P8 Verification & admin console | Y | Review | admin/03-marketplace.html | Review with Claude: admin/03-marketplace.html | All review comments fixed | Code review | design/screens/admin/03-marketplace.html | 1 | Not started |  | Not requested
730 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/04-trust.html | Screen A-04a — Verification queue | Matches frame; tokens only; loading/error states | UI | design/screens/admin/04-trust.html | 1 | Not started |  | Not requested
731 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/04-trust.html | Screen A-04b — Verification review | Matches frame; tokens only; loading/error states | UI | design/screens/admin/04-trust.html | 1 | Not started |  | Not requested
732 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/04-trust.html | Screen A-04c — Revoke a verified check (two admins) | Matches frame; tokens only; loading/error states | UI | design/screens/admin/04-trust.html | 1 | Not started |  | Not requested
733 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/04-trust.html | Screen A-04d — Dispute queue | Matches frame; tokens only; loading/error states | UI | design/screens/admin/04-trust.html | 1 | Not started |  | Not requested
734 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/04-trust.html | Screen A-04e — Dispute investigation + decision | Matches frame; tokens only; loading/error states | UI | design/screens/admin/04-trust.html | 1 | Not started |  | Not requested
735 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/04-trust.html | Screen A-04f — Resolved dispute · action status & retry | Matches frame; tokens only; loading/error states | UI | design/screens/admin/04-trust.html | 1 | Not started |  | Not requested
736 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/04-trust.html | Screen A-04g — Review moderation | Matches frame; tokens only; loading/error states | UI | design/screens/admin/04-trust.html | 1 | Not started |  | Not requested
737 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/04-trust.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/admin/04-trust.html | 1 | Not started |  | Not requested
738 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/04-trust.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/admin/04-trust.html | 1 | Not started |  | Not requested
739 |  |  |  | P8 Verification & admin console | Y | Review | admin/04-trust.html | Review with Claude: admin/04-trust.html | All review comments fixed | Code review | design/screens/admin/04-trust.html | 1 | Not started |  | Not requested
740 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/06-config.html | Screen A-06a — Catalog · trade editor | Matches frame; tokens only; loading/error states | UI | design/screens/admin/06-config.html | 1 | Not started |  | Not requested
741 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/06-config.html | Screen A-06b — Edit common problem (en/bn/hi + keywords) · fixed (was "Edit service") | Matches frame; tokens only; loading/error states | UI | design/screens/admin/06-config.html | 1 | Not started |  | Not requested
742 |  |  |  | P8 Verification & admin console | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
743 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/06-config.html | Screen A-06c — Service zones | Matches frame; tokens only; loading/error states | UI | design/screens/admin/06-config.html | 1 | Not started |  | Not requested
744 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/06-config.html | Screen A-06d — Notifications delivery log · fixed (was "Communications") | Matches frame; tokens only; loading/error states | UI | design/screens/admin/06-config.html | 1 | Not started |  | Not requested
745 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/06-config.html | Screen A-06e — Outbox · dead events (system health) · fixed (was "System health") | Matches frame; tokens only; loading/error states | UI | design/screens/admin/06-config.html | 1 | Not started |  | Not requested
746 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/06-config.html | Screen A-06f — Audit log | Matches frame; tokens only; loading/error states | UI | design/screens/admin/06-config.html | 1 | Not started |  | Not requested
747 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/06-config.html | Screen A-06g — Staff (admin users) + step-up code | Matches frame; tokens only; loading/error states | UI | design/screens/admin/06-config.html | 1 | Not started |  | Not requested
748 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/06-config.html | Screen A-06h — Roles & permissions (read-only matrix) | Matches frame; tokens only; loading/error states | UI | design/screens/admin/06-config.html | 1 | Not started |  | Not requested
749 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/06-config.html | Screen A-06i — Platform settings (read-only) | Matches frame; tokens only; loading/error states | UI | design/screens/admin/06-config.html | 1 | Not started |  | Not requested
750 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/06-config.html | Screen A-06j — Reason codes (read-only) | Matches frame; tokens only; loading/error states | UI | design/screens/admin/06-config.html | 1 | Not started |  | Not requested
751 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/06-config.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/admin/06-config.html | 1 | Not started |  | Not requested
752 |  |  |  | P8 Verification & admin console | Y | Admin web | admin/06-config.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/admin/06-config.html | 1 | Not started |  | Not requested
753 |  |  |  | P8 Verification & admin console | Y | Review | admin/06-config.html | Review with Claude: admin/06-config.html | All review comments fixed | Code review | design/screens/admin/06-config.html | 1 | Not started |  | Not requested
754 |  |  |  | P8 Verification & admin console | Y | Review | milestone | Milestone demo: Worker uploads ID; admin logs in with MFA, approves worker, looks up users, edits catalog | Demo recorded; README updated | Demo | plan/ | 1 | Not started |  | Not requested
755 |  |  |  | P9 Pilot release (cash-only) | Y | Testing | all | End-to-end smoke script: request → pick → job → cash → review | Script passes on staging | E2E testing |  | 1 | Not started |  | Not requested
756 |  |  |  | P9 Pilot release (cash-only) | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
757 |  |  |  | P9 Pilot release (cash-only) | Y | Testing | all | Fix bugs from smoke test (1/2) | No blocker bugs open |  |  | 1 | Not started |  | Not requested
758 |  |  |  | P9 Pilot release (cash-only) | Y | Testing | all | Fix bugs from smoke test (2/2) | No blocker bugs open |  |  | 1 | Not started |  | Not requested
759 |  |  |  | P9 Pilot release (cash-only) | Y | DevOps | infra | Dockerfile + production docker-compose | Image builds in CI | Docker | operations/02 | 1 | Not started |  | Not requested
760 |  |  |  | P9 Pilot release (cash-only) | Y | DevOps | infra | VM setup: firewall, Docker, Caddy/Nginx HTTPS | API reachable over HTTPS | Linux ops | operations/02 | 1 | Not started |  | Not requested
761 |  |  |  | P9 Pilot release (cash-only) | Y | DevOps | infra | Deploy from CI to the VM | Push to main deploys | CD | operations/02 | 1 | Not started |  | Not requested
762 |  |  |  | P9 Pilot release (cash-only) | Y | DevOps | infra | Database backups + restore test | Restore works on a scratch DB | Backups |  | 1 | Not started |  | Not requested
763 |  |  |  | P9 Pilot release (cash-only) | Y | DevOps | infra | Logs + health checks + uptime alert | Alert fires when API stops |  |  | 1 | Not started |  | Not requested
764 |  |  |  | P9 Pilot release (cash-only) | Y | Security | all | Security checklist pass (security/02) (1/2) | Checklist items ticked | AppSec | security/02 | 1 | Not started |  | Not requested
765 |  |  |  | P9 Pilot release (cash-only) | Y | Security | all | Security checklist pass (security/02) (2/2) | Checklist items ticked | AppSec | security/02 | 1 | Not started |  | Not requested
766 |  |  |  | P9 Pilot release (cash-only) | Y | DevOps | apps | EAS build: Android customer + worker APKs | APKs install on phones | EAS |  | 1 | Not started |  | Not requested
767 |  |  |  | P9 Pilot release (cash-only) | Y | DevOps | apps | Play Console internal testing track for both apps | Testers can install | Play Store |  | 1 | Not started |  | Not requested
768 |  |  |  | P9 Pilot release (cash-only) | Y | Ops | all | Bengali + Hindi string review with a native speaker | Corrections merged |  |  | 1 | Not started |  | Not requested
769 |  |  |  | P9 Pilot release (cash-only) | Y | Ops | all | Seed real trades, problems, rates for the pilot zone | Catalog looks right in app |  |  | 1 | Not started |  | Not requested
770 |  |  |  | P9 Pilot release (cash-only) | Y | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
771 |  |  |  | P9 Pilot release (cash-only) | Y | Ops | all | Onboard and verify first 5 workers | 5 ACTIVE workers |  |  | 1 | Not started |  | Not requested
772 |  |  |  | P9 Pilot release (cash-only) | Y | Ops | all | Pilot launch: first real jobs; write a feedback log | First paid job done |  |  | 1 | Not started |  | Not requested
773 |  |  |  | P9 Pilot release (cash-only) | Y | Review | milestone | Milestone demo: Running on a VM with HTTPS + backups; Android builds with real workers in one Howrah zone | Demo recorded; README updated | Demo | plan/ | 1 | Not started |  | Not requested
774 |  |  |  | P10 Online payments & payouts | N | Learning | LLD-011 | Read LLD-011: Online Payment — Provider Checkout, Webhooks, Refunds, Reconciliation; list questions | Can explain the flow and tables | Domain | lld/lld-011-online-payment-webhooks-refunds.md | 1 | Not started |  | Not requested
775 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-011 | Flyway migration: tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-011-online-payment-webhooks-refunds.md §3 | 1 | Not started |  | Not requested
776 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-011 | Entities + repositories + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-011-online-payment-webhooks-refunds.md §3 | 1 | Not started |  | Not requested
777 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-011 | Payment provider port + Razorpay adapter (sandbox) (ADR 0007) | Unit tests cover happy + failure paths | Domain logic | lld/lld-011-online-payment-webhooks-refunds.md §2/§5/§6 | 1 | Not started |  | Not requested
778 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-011 | Checkout order create + client hand-off | Unit tests cover happy + failure paths | Domain logic | lld/lld-011-online-payment-webhooks-refunds.md §2/§5/§6 | 1 | Not started |  | Not requested
779 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-011 | Webhook endpoint: signature check, idempotent | Unit tests cover happy + failure paths | Domain logic | lld/lld-011-online-payment-webhooks-refunds.md §2/§5/§6 | 1 | Not started |  | Not requested
780 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-011 | Payment state machine | Unit tests cover happy + failure paths | Domain logic | lld/lld-011-online-payment-webhooks-refunds.md §2/§5/§6 | 1 | Not started |  | Not requested
781 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-011 | Refunds: full + pro-rata | Unit tests cover happy + failure paths | Domain logic | lld/lld-011-online-payment-webhooks-refunds.md §2/§5/§6 | 1 | Not started |  | Not requested
782 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-011 | Daily reconciliation job | Unit tests cover happy + failure paths | Domain logic | lld/lld-011-online-payment-webhooks-refunds.md §2/§5/§6 | 1 | Not started |  | Not requested
783 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-011 | API POST /api/v1/jobs/{id}/payments/online | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-011-online-payment-webhooks-refunds.md §4 | 1 | Not started |  | Not requested
784 |  |  |  | P10 Online payments & payouts | N | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
785 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-011 | API GET /api/v1/payments/{id} | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-011-online-payment-webhooks-refunds.md §4 | 1 | Not started |  | Not requested
786 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-011 | API POST /api/v1/service-requests/{id}/pay-advance | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-011-online-payment-webhooks-refunds.md §4 | 1 | Not started |  | Not requested
787 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-011 | API POST /api/v1/payments/webhooks/{provider} | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-011-online-payment-webhooks-refunds.md §4 | 1 | Not started |  | Not requested
788 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-011 | API GET /api/v1/admin/payments | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-011-online-payment-webhooks-refunds.md §4 | 1 | Not started |  | Not requested
789 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-011 | API POST /api/v1/admin/payments/{id}/refunds | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-011-online-payment-webhooks-refunds.md §4 | 1 | Not started |  | Not requested
790 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-011 | Events: publish/consume via outbox; check error handling §7 | Outbox rows written; consumer idempotent | Events | lld/lld-011-online-payment-webhooks-refunds.md §7 | 1 | Not started |  | Not requested
791 |  |  |  | P10 Online payments & payouts | N | Review | LLD-011 | Module review with Claude: LLD-011 full diff + test plan §10 | All review comments fixed | Code review | lld/lld-011-online-payment-webhooks-refunds.md §10 | 1 | Not started |  | Not requested
792 |  |  |  | P10 Online payments & payouts | N | Learning | LLD-019 | Read LLD-019: Worker Payout Accounts, Payouts and Dues Collection; list questions | Can explain the flow and tables | Domain | lld/lld-019-worker-payouts.md | 1 | Not started |  | Not requested
793 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-019 | Flyway migration (1/2): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-019-worker-payouts.md §3 | 1 | Not started |  | Not requested
794 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-019 | Flyway migration (2/2): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-019-worker-payouts.md §3 | 1 | Not started |  | Not requested
795 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-019 | Entities + repositories (1/2) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-019-worker-payouts.md §3 | 1 | Not started |  | Not requested
796 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-019 | Entities + repositories (2/2) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-019-worker-payouts.md §3 | 1 | Not started |  | Not requested
797 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-019 | Payout account + penny-drop verify (sandbox) | Unit tests cover happy + failure paths | Domain logic | lld/lld-019-worker-payouts.md §2/§5/§6 | 1 | Not started |  | Not requested
798 |  |  |  | P10 Online payments & payouts | N | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
799 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-019 | Payout batch job from ledger balance | Unit tests cover happy + failure paths | Domain logic | lld/lld-019-worker-payouts.md §2/§5/§6 | 1 | Not started |  | Not requested
800 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-019 | Dues collection by UPI | Unit tests cover happy + failure paths | Domain logic | lld/lld-019-worker-payouts.md §2/§5/§6 | 1 | Not started |  | Not requested
801 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-019 | API POST /api/v1/worker/payout-accounts | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-019-worker-payouts.md §4 | 1 | Not started |  | Not requested
802 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-019 | API GET /api/v1/worker/payout-accounts | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-019-worker-payouts.md §4 | 1 | Not started |  | Not requested
803 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-019 | API GET /api/v1/worker/payouts | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-019-worker-payouts.md §4 | 1 | Not started |  | Not requested
804 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-019 | API GET /api/v1/worker/payouts/{id} | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-019-worker-payouts.md §4 | 1 | Not started |  | Not requested
805 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-019 | API POST /api/v1/worker/dues/pay | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-019-worker-payouts.md §4 | 1 | Not started |  | Not requested
806 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-019 | API GET /api/v1/admin/payouts | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-019-worker-payouts.md §4 | 1 | Not started |  | Not requested
807 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-019 | API POST /api/v1/admin/workers/{id}/payout-hold | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-019-worker-payouts.md §4 | 1 | Not started |  | Not requested
808 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-019 | API DELETE /api/v1/admin/workers/{id}/payout-hold | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-019-worker-payouts.md §4 | 1 | Not started |  | Not requested
809 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-019 | API POST /api/v1/admin/payout-accounts/{id}/approve | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-019-worker-payouts.md §4 | 1 | Not started |  | Not requested
810 |  |  |  | P10 Online payments & payouts | N | Backend | LLD-019 | Events: publish/consume via outbox; check error handling §7 | Outbox rows written; consumer idempotent | Events | lld/lld-019-worker-payouts.md §7 | 1 | Not started |  | Not requested
811 |  |  |  | P10 Online payments & payouts | N | Review | LLD-019 | Module review with Claude: LLD-019 full diff + test plan §10 | All review comments fixed | Code review | lld/lld-019-worker-payouts.md §10 | 1 | Not started |  | Not requested
812 |  |  |  | P10 Online payments & payouts | N | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
813 |  |  |  | P10 Online payments & payouts | N | Learning | — | Razorpay test mode: checkout flow and webhooks | Notes in learning log; small sample committed | Payments | adr/0007 | 1 | Not started |  | Not requested
814 |  |  |  | P10 Online payments & payouts | N | App-Customer | customer/04-advance-payment.html | Screen C-04a — Provider checkout (UPI intent) | Matches frame; tokens only; loading/error states | UI | design/screens/customer/04-advance-payment.html | 1 | Not started |  | Not requested
815 |  |  |  | P10 Online payments & payouts | N | App-Customer | customer/04-advance-payment.html | Screen C-04b — Payment pending | Matches frame; tokens only; loading/error states | UI | design/screens/customer/04-advance-payment.html | 1 | Not started |  | Not requested
816 |  |  |  | P10 Online payments & payouts | N | App-Customer | customer/04-advance-payment.html | Screen C-04c — Advance paid → finding workers | Matches frame; tokens only; loading/error states | UI | design/screens/customer/04-advance-payment.html | 1 | Not started |  | Not requested
817 |  |  |  | P10 Online payments & payouts | N | App-Customer | customer/04-advance-payment.html | Screen C-04d — Payment failed · retry | Matches frame; tokens only; loading/error states | UI | design/screens/customer/04-advance-payment.html | 1 | Not started |  | Not requested
818 |  |  |  | P10 Online payments & payouts | N | App-Customer | customer/04-advance-payment.html | Screen C-04e — Payment window closed | Matches frame; tokens only; loading/error states | UI | design/screens/customer/04-advance-payment.html | 1 | Not started |  | Not requested
819 |  |  |  | P10 Online payments & payouts | N | App-Customer | customer/04-advance-payment.html | Screen C-04f — Late payment → refunded | Matches frame; tokens only; loading/error states | UI | design/screens/customer/04-advance-payment.html | 1 | Not started |  | Not requested
820 |  |  |  | P10 Online payments & payouts | N | App-Customer | customer/04-advance-payment.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/customer/04-advance-payment.html | 1 | Not started |  | Not requested
821 |  |  |  | P10 Online payments & payouts | N | App-Customer | customer/04-advance-payment.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/customer/04-advance-payment.html | 1 | Not started |  | Not requested
822 |  |  |  | P10 Online payments & payouts | N | Review | customer/04-advance-payment.html | Review with Claude: customer/04-advance-payment.html | All review comments fixed | Code review | design/screens/customer/04-advance-payment.html | 1 | Not started |  | Not requested
823 |  |  |  | P10 Online payments & payouts | N | App-Worker | worker/04-bank-profile.html | Screen W-04a — Bank account | Matches frame; tokens only; loading/error states | UI | design/screens/worker/04-bank-profile.html | 1 | Not started |  | Not requested
824 |  |  |  | P10 Online payments & payouts | N | App-Worker | worker/04-bank-profile.html | Screen W-04b — Verifying (penny drop) | Matches frame; tokens only; loading/error states | UI | design/screens/worker/04-bank-profile.html | 1 | Not started |  | Not requested
825 |  |  |  | P10 Online payments & payouts | N | App-Worker | worker/04-bank-profile.html | Screen W-04c — Under review (name check) | Matches frame; tokens only; loading/error states | UI | design/screens/worker/04-bank-profile.html | 1 | Not started |  | Not requested
826 |  |  |  | P10 Online payments & payouts | N | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
827 |  |  |  | P10 Online payments & payouts | N | App-Worker | worker/04-bank-profile.html | Screen W-04d — Failed | Matches frame; tokens only; loading/error states | UI | design/screens/worker/04-bank-profile.html | 1 | Not started |  | Not requested
828 |  |  |  | P10 Online payments & payouts | N | App-Worker | worker/04-bank-profile.html | Screen W-04f — Profile hub | Matches frame; tokens only; loading/error states | UI | design/screens/worker/04-bank-profile.html | 1 | Not started |  | Not requested
829 |  |  |  | P10 Online payments & payouts | N | App-Worker | worker/04-bank-profile.html | Screen W-04g — Edit profile | Matches frame; tokens only; loading/error states | UI | design/screens/worker/04-bank-profile.html | 1 | Not started |  | Not requested
830 |  |  |  | P10 Online payments & payouts | N | App-Worker | worker/04-bank-profile.html | Screen W-04h — Settings & security | Matches frame; tokens only; loading/error states | UI | design/screens/worker/04-bank-profile.html | 1 | Not started |  | Not requested
831 |  |  |  | P10 Online payments & payouts | N | App-Worker | worker/04-bank-profile.html | Screen W-04i — Delete account | Matches frame; tokens only; loading/error states | UI | design/screens/worker/04-bank-profile.html | 1 | Not started |  | Not requested
832 |  |  |  | P10 Online payments & payouts | N | App-Worker | worker/04-bank-profile.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/worker/04-bank-profile.html | 1 | Not started |  | Not requested
833 |  |  |  | P10 Online payments & payouts | N | App-Worker | worker/04-bank-profile.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/worker/04-bank-profile.html | 1 | Not started |  | Not requested
834 |  |  |  | P10 Online payments & payouts | N | Review | worker/04-bank-profile.html | Review with Claude: worker/04-bank-profile.html | All review comments fixed | Code review | design/screens/worker/04-bank-profile.html | 1 | Not started |  | Not requested
835 |  |  |  | P10 Online payments & payouts | N | Admin web | admin/05-money.html | Screen A-05a — Payments & refunds | Matches frame; tokens only; loading/error states | UI | design/screens/admin/05-money.html | 1 | Not started |  | Not requested
836 |  |  |  | P10 Online payments & payouts | N | Admin web | admin/05-money.html | Screen A-05b — Refund dialog (pro-rata preview) | Matches frame; tokens only; loading/error states | UI | design/screens/admin/05-money.html | 1 | Not started |  | Not requested
837 |  |  |  | P10 Online payments & payouts | N | Admin web | admin/05-money.html | Screen A-05c — Queues · stuck refunds, parked provider events, disputed cash | Matches frame; tokens only; loading/error states | UI | design/screens/admin/05-money.html | 1 | Not started |  | Not requested
838 |  |  |  | P10 Online payments & payouts | N | Admin web | admin/05-money.html | Screen A-05d — Payout accounts review + payout hold | Matches frame; tokens only; loading/error states | UI | design/screens/admin/05-money.html | 1 | Not started |  | Not requested
839 |  |  |  | P10 Online payments & payouts | N | Admin web | admin/05-money.html | Screen A-05e — Ledger · worker balance & manual adjustment | Matches frame; tokens only; loading/error states | UI | design/screens/admin/05-money.html | 1 | Not started |  | Not requested
840 |  |  |  | P10 Online payments & payouts | N | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
841 |  |  |  | P10 Online payments & payouts | N | Admin web | admin/05-money.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/admin/05-money.html | 1 | Not started |  | Not requested
842 |  |  |  | P10 Online payments & payouts | N | Admin web | admin/05-money.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/admin/05-money.html | 1 | Not started |  | Not requested
843 |  |  |  | P10 Online payments & payouts | N | Review | admin/05-money.html | Review with Claude: admin/05-money.html | All review comments fixed | Code review | design/screens/admin/05-money.html | 1 | Not started |  | Not requested
844 |  |  |  | P10 Online payments & payouts | N | Review | milestone | Milestone demo: Advance + online bill payment via provider sandbox, refunds, worker payouts | Demo recorded; README updated | Demo | plan/ | 1 | Not started |  | Not requested
845 |  |  |  | P11 Quotes, disputes, realtime | N | Learning | LLD-017 | Read LLD-017: Quotes, Additional Work and Material Bills; list questions | Can explain the flow and tables | Domain | lld/lld-017-quotes-additional-work-material.md | 1 | Not started |  | Not requested
846 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-017 | Flyway migration (1/2): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-017-quotes-additional-work-material.md §3 | 1 | Not started |  | Not requested
847 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-017 | Flyway migration (2/2): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-017-quotes-additional-work-material.md §3 | 1 | Not started |  | Not requested
848 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-017 | Entities + repositories (1/2) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-017-quotes-additional-work-material.md §3 | 1 | Not started |  | Not requested
849 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-017 | Entities + repositories (2/2) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-017-quotes-additional-work-material.md §3 | 1 | Not started |  | Not requested
850 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-017 | Quote state machine: sent/approved/rejected | Unit tests cover happy + failure paths | Domain logic | lld/lld-017-quotes-additional-work-material.md §2/§5/§6 | 1 | Not started |  | Not requested
851 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-017 | Material bill with photo | Unit tests cover happy + failure paths | Domain logic | lld/lld-017-quotes-additional-work-material.md §2/§5/§6 | 1 | Not started |  | Not requested
852 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-017 | Bill total recalculation in paise | Unit tests cover happy + failure paths | Domain logic | lld/lld-017-quotes-additional-work-material.md §2/§5/§6 | 1 | Not started |  | Not requested
853 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-017 | API POST /api/v1/jobs/{id}/quotes | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-017-quotes-additional-work-material.md §4 | 1 | Not started |  | Not requested
854 |  |  |  | P11 Quotes, disputes, realtime | N | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
855 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-017 | API GET /api/v1/jobs/{id}/quotes | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-017-quotes-additional-work-material.md §4 | 1 | Not started |  | Not requested
856 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-017 | API GET /api/v1/quotes/{id} | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-017-quotes-additional-work-material.md §4 | 1 | Not started |  | Not requested
857 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-017 | API POST /api/v1/quotes/{id}/revise | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-017-quotes-additional-work-material.md §4 | 1 | Not started |  | Not requested
858 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-017 | API POST /api/v1/quotes/{id}/withdraw | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-017-quotes-additional-work-material.md §4 | 1 | Not started |  | Not requested
859 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-017 | API POST /api/v1/quotes/{id}/accept | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-017-quotes-additional-work-material.md §4 | 1 | Not started |  | Not requested
860 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-017 | API POST /api/v1/quotes/{id}/reject | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-017-quotes-additional-work-material.md §4 | 1 | Not started |  | Not requested
861 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-017 | API POST /api/v1/jobs/{id}/material-bills | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-017-quotes-additional-work-material.md §4 | 1 | Not started |  | Not requested
862 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-017 | API GET /api/v1/jobs/{id}/material-bills | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-017-quotes-additional-work-material.md §4 | 1 | Not started |  | Not requested
863 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-017 | API POST /api/v1/material-bills/{id}/acknowledge | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-017-quotes-additional-work-material.md §4 | 1 | Not started |  | Not requested
864 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-017 | API POST /api/v1/material-bills/{id}/reject | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-017-quotes-additional-work-material.md §4 | 1 | Not started |  | Not requested
865 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-017 | API POST /api/v1/material-bills/{id}/void | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-017-quotes-additional-work-material.md §4 | 1 | Not started |  | Not requested
866 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-017 | Events: publish/consume via outbox; check error handling §7 | Outbox rows written; consumer idempotent | Events | lld/lld-017-quotes-additional-work-material.md §7 | 1 | Not started |  | Not requested
867 |  |  |  | P11 Quotes, disputes, realtime | N | Review | LLD-017 | Module review with Claude: LLD-017 full diff + test plan §10 | All review comments fixed | Code review | lld/lld-017-quotes-additional-work-material.md §10 | 1 | Not started |  | Not requested
868 |  |  |  | P11 Quotes, disputes, realtime | N | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
869 |  |  |  | P11 Quotes, disputes, realtime | N | Learning | LLD-018 | Read LLD-018: Disputes — Cases, Evidence, Resolution Actions; list questions | Can explain the flow and tables | Domain | lld/lld-018-disputes.md | 1 | Not started |  | Not requested
870 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-018 | Flyway migration (1/2): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-018-disputes.md §3 | 1 | Not started |  | Not requested
871 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-018 | Flyway migration (2/2): tables from §3 | Migration runs; constraints match the LLD | SQL / Flyway | lld/lld-018-disputes.md §3 | 1 | Not started |  | Not requested
872 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-018 | Entities + repositories (1/2) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-018-disputes.md §3 | 1 | Not started |  | Not requested
873 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-018 | Entities + repositories (2/2) + Testcontainers repo test | Repo test green on real PostgreSQL | JPA | lld/lld-018-disputes.md §3 | 1 | Not started |  | Not requested
874 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-018 | Dispute case state machine | Unit tests cover happy + failure paths | Domain logic | lld/lld-018-disputes.md §2/§5/§6 | 1 | Not started |  | Not requested
875 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-018 | Evidence attachments via media | Unit tests cover happy + failure paths | Domain logic | lld/lld-018-disputes.md §2/§5/§6 | 1 | Not started |  | Not requested
876 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-018 | Resolution actions: refund / adjust ledger / warn | Unit tests cover happy + failure paths | Domain logic | lld/lld-018-disputes.md §2/§5/§6 | 1 | Not started |  | Not requested
877 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-018 | API POST /api/v1/disputes | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-018-disputes.md §4 | 1 | Not started |  | Not requested
878 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-018 | API GET /api/v1/disputes | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-018-disputes.md §4 | 1 | Not started |  | Not requested
879 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-018 | API GET /api/v1/disputes/{id} | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-018-disputes.md §4 | 1 | Not started |  | Not requested
880 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-018 | API POST /api/v1/disputes/{id}/statements | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-018-disputes.md §4 | 1 | Not started |  | Not requested
881 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-018 | API POST /api/v1/disputes/{id}/withdraw | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-018-disputes.md §4 | 1 | Not started |  | Not requested
882 |  |  |  | P11 Quotes, disputes, realtime | N | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
883 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-018 | API GET /api/v1/admin/disputes | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-018-disputes.md §4 | 1 | Not started |  | Not requested
884 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-018 | API GET /api/v1/admin/disputes/{id} | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-018-disputes.md §4 | 1 | Not started |  | Not requested
885 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-018 | API POST /api/v1/admin/disputes | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-018-disputes.md §4 | 1 | Not started |  | Not requested
886 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-018 | API POST /api/v1/admin/disputes/{id}/claim | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-018-disputes.md §4 | 1 | Not started |  | Not requested
887 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-018 | API POST /api/v1/admin/disputes/{id}/notes | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-018-disputes.md §4 | 1 | Not started |  | Not requested
888 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-018 | API POST /api/v1/admin/disputes/{id}/messages | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-018-disputes.md §4 | 1 | Not started |  | Not requested
889 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-018 | API POST /api/v1/admin/disputes/{id}/resolve | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-018-disputes.md §4 | 1 | Not started |  | Not requested
890 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-018 | API POST /api/v1/admin/disputes/{id}/reject | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-018-disputes.md §4 | 1 | Not started |  | Not requested
891 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-018 | API POST /api/v1/admin/disputes/{id}/actions/{actionId}/retry | Controller + validation + API test (happy + 1 error) | Spring Web | lld/lld-018-disputes.md §4 | 1 | Not started |  | Not requested
892 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-018 | Events: publish/consume via outbox; check error handling §7 | Outbox rows written; consumer idempotent | Events | lld/lld-018-disputes.md §7 | 1 | Not started |  | Not requested
893 |  |  |  | P11 Quotes, disputes, realtime | N | Review | LLD-018 | Module review with Claude: LLD-018 full diff + test plan §10 | All review comments fixed | Code review | lld/lld-018-disputes.md §10 | 1 | Not started |  | Not requested
894 |  |  |  | P11 Quotes, disputes, realtime | N | Learning | LLD-021 | Read LLD-021: Realtime Updates over WebSocket; list questions | Can explain the flow and tables | Domain | lld/lld-021-realtime-updates.md | 1 | Not started |  | Not requested
895 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-021 | Spring WebSocket + STOMP config, JWT on CONNECT | Unit tests cover happy + failure paths | Domain logic | lld/lld-021-realtime-updates.md §2/§5/§6 | 1 | Not started |  | Not requested
896 |  |  |  | P11 Quotes, disputes, realtime | N | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
897 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-021 | Per-user queue + event → message mapping | Unit tests cover happy + failure paths | Domain logic | lld/lld-021-realtime-updates.md §2/§5/§6 | 1 | Not started |  | Not requested
898 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-021 | Revoke on logout; reconnect contract test | Unit tests cover happy + failure paths | Domain logic | lld/lld-021-realtime-updates.md §2/§5/§6 | 1 | Not started |  | Not requested
899 |  |  |  | P11 Quotes, disputes, realtime | N | Backend | LLD-021 | Events: publish/consume via outbox; check error handling §7 | Outbox rows written; consumer idempotent | Events | lld/lld-021-realtime-updates.md §7 | 1 | Not started |  | Not requested
900 |  |  |  | P11 Quotes, disputes, realtime | N | Review | LLD-021 | Module review with Claude: LLD-021 full diff + test plan §10 | All review comments fixed | Code review | lld/lld-021-realtime-updates.md §10 | 1 | Not started |  | Not requested
901 |  |  |  | P11 Quotes, disputes, realtime | N | Learning | — | STOMP over WebSocket client in React Native | Notes in learning log; small sample committed | WebSocket |  | 1 | Not started |  | Not requested
902 |  |  |  | P11 Quotes, disputes, realtime | N | App-Shared | api | Realtime client: connect with JWT, reconnect, update query cache | Customer sees check-in live | WebSocket | lld-021 | 1 | Not started |  | Not requested
903 |  |  |  | P11 Quotes, disputes, realtime | N | App-Worker | worker/07-quotes-cash.html | Screen W-07a — Extra work price · build | Matches frame; tokens only; loading/error states | UI | design/screens/worker/07-quotes-cash.html | 1 | Not started |  | Not requested
904 |  |  |  | P11 Quotes, disputes, realtime | N | App-Worker | worker/07-quotes-cash.html | Screen W-07b — Price sent · waiting | Matches frame; tokens only; loading/error states | UI | design/screens/worker/07-quotes-cash.html | 1 | Not started |  | Not requested
905 |  |  |  | P11 Quotes, disputes, realtime | N | App-Worker | worker/07-quotes-cash.html | Screen W-07c — Price approved | Matches frame; tokens only; loading/error states | UI | design/screens/worker/07-quotes-cash.html | 1 | Not started |  | Not requested
906 |  |  |  | P11 Quotes, disputes, realtime | N | App-Worker | worker/07-quotes-cash.html | Screen W-07d — Price not approved | Matches frame; tokens only; loading/error states | UI | design/screens/worker/07-quotes-cash.html | 1 | Not started |  | Not requested
907 |  |  |  | P11 Quotes, disputes, realtime | N | App-Worker | worker/07-quotes-cash.html | Screen W-07e — Shop bill · add | Matches frame; tokens only; loading/error states | UI | design/screens/worker/07-quotes-cash.html | 1 | Not started |  | Not requested
908 |  |  |  | P11 Quotes, disputes, realtime | N | App-Worker | worker/07-quotes-cash.html | Screen W-07f — Shop bills · covered vs needs OK | Matches frame; tokens only; loading/error states | UI | design/screens/worker/07-quotes-cash.html | 1 | Not started |  | Not requested
909 |  |  |  | P11 Quotes, disputes, realtime | N | App-Worker | worker/07-quotes-cash.html | Screen W-07g — Finish job | Matches frame; tokens only; loading/error states | UI | design/screens/worker/07-quotes-cash.html | 1 | Not started |  | Not requested
910 |  |  |  | P11 Quotes, disputes, realtime | N | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
911 |  |  |  | P11 Quotes, disputes, realtime | N | App-Worker | worker/07-quotes-cash.html | Screen W-07h — Work done · waiting for customer | Matches frame; tokens only; loading/error states | UI | design/screens/worker/07-quotes-cash.html | 1 | Not started |  | Not requested
912 |  |  |  | P11 Quotes, disputes, realtime | N | App-Worker | worker/07-quotes-cash.html | Screen W-07i — Bill for the job | Matches frame; tokens only; loading/error states | UI | design/screens/worker/07-quotes-cash.html | 1 | Not started |  | Not requested
913 |  |  |  | P11 Quotes, disputes, realtime | N | App-Worker | worker/07-quotes-cash.html | Screen W-07j — Customer paid me cash | Matches frame; tokens only; loading/error states | UI | design/screens/worker/07-quotes-cash.html | 1 | Not started |  | Not requested
914 |  |  |  | P11 Quotes, disputes, realtime | N | App-Worker | worker/07-quotes-cash.html | Screen W-07k — Cash · waiting for customer | Matches frame; tokens only; loading/error states | UI | design/screens/worker/07-quotes-cash.html | 1 | Not started |  | Not requested
915 |  |  |  | P11 Quotes, disputes, realtime | N | App-Worker | worker/07-quotes-cash.html | Screen W-07l — Cash · confirmed | Matches frame; tokens only; loading/error states | UI | design/screens/worker/07-quotes-cash.html | 1 | Not started |  | Not requested
916 |  |  |  | P11 Quotes, disputes, realtime | N | App-Worker | worker/07-quotes-cash.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/worker/07-quotes-cash.html | 1 | Not started |  | Not requested
917 |  |  |  | P11 Quotes, disputes, realtime | N | App-Worker | worker/07-quotes-cash.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/worker/07-quotes-cash.html | 1 | Not started |  | Not requested
918 |  |  |  | P11 Quotes, disputes, realtime | N | Review | worker/07-quotes-cash.html | Review with Claude: worker/07-quotes-cash.html | All review comments fixed | Code review | design/screens/worker/07-quotes-cash.html | 1 | Not started |  | Not requested
919 |  |  |  | P11 Quotes, disputes, realtime | N | App-Customer | customer/13-support.html | Screen C-13a — Help & support | Matches frame; tokens only; loading/error states | UI | design/screens/customer/13-support.html | 1 | Not started |  | Not requested
920 |  |  |  | P11 Quotes, disputes, realtime | N | App-Customer | customer/13-support.html | Screen C-13b — Help article | Matches frame; tokens only; loading/error states | UI | design/screens/customer/13-support.html | 1 | Not started |  | Not requested
921 |  |  |  | P11 Quotes, disputes, realtime | N | App-Customer | customer/13-support.html | Screen C-13c — Report a problem · 1 What | Matches frame; tokens only; loading/error states | UI | design/screens/customer/13-support.html | 1 | Not started |  | Not requested
922 |  |  |  | P11 Quotes, disputes, realtime | N | App-Customer | customer/13-support.html | Screen C-13d — Report a problem · 2 Details | Matches frame; tokens only; loading/error states | UI | design/screens/customer/13-support.html | 1 | Not started |  | Not requested
923 |  |  |  | P11 Quotes, disputes, realtime | N | App-Customer | customer/13-support.html | Screen C-13e — Report a problem · window closed | Matches frame; tokens only; loading/error states | UI | design/screens/customer/13-support.html | 1 | Not started |  | Not requested
924 |  |  |  | P11 Quotes, disputes, realtime | N | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
925 |  |  |  | P11 Quotes, disputes, realtime | N | App-Customer | customer/13-support.html | Screen C-13f — Your report · waiting for reply | Matches frame; tokens only; loading/error states | UI | design/screens/customer/13-support.html | 1 | Not started |  | Not requested
926 |  |  |  | P11 Quotes, disputes, realtime | N | App-Customer | customer/13-support.html | Screen C-13g — Your report · decided | Matches frame; tokens only; loading/error states | UI | design/screens/customer/13-support.html | 1 | Not started |  | Not requested
927 |  |  |  | P11 Quotes, disputes, realtime | N | App-Customer | customer/13-support.html | Screen C-13h — Grievance | Matches frame; tokens only; loading/error states | UI | design/screens/customer/13-support.html | 1 | Not started |  | Not requested
928 |  |  |  | P11 Quotes, disputes, realtime | N | App-Customer | customer/13-support.html | Screen C-13i — Grievance sent | Matches frame; tokens only; loading/error states | UI | design/screens/customer/13-support.html | 1 | Not started |  | Not requested
929 |  |  |  | P11 Quotes, disputes, realtime | N | App-Customer | customer/13-support.html | Wire screens to the API (queries + mutations) | Real data from local backend | Data fetching | design/screens/customer/13-support.html | 1 | Not started |  | Not requested
930 |  |  |  | P11 Quotes, disputes, realtime | N | App-Customer | customer/13-support.html | en/bn/hi strings + test on an Android phone | No missing strings; works on device | i18n | design/screens/customer/13-support.html | 1 | Not started |  | Not requested
931 |  |  |  | P11 Quotes, disputes, realtime | N | Review | customer/13-support.html | Review with Claude: customer/13-support.html | All review comments fixed | Code review | design/screens/customer/13-support.html | 1 | Not started |  | Not requested
932 |  |  |  | P11 Quotes, disputes, realtime | N | Review | milestone | Milestone demo: Extra work quotes + material bills; disputes end to end; live updates without refresh | Demo recorded; README updated | Demo | plan/ | 1 | Not started |  | Not requested
933 |  |  |  | P12 Full MVP release | N | Testing | all | Full regression on both apps + admin (1/3) | Regression list passes |  |  | 1 | Not started |  | Not requested
934 |  |  |  | P12 Full MVP release | N | Testing | all | Full regression on both apps + admin (2/3) | Regression list passes |  |  | 1 | Not started |  | Not requested
935 |  |  |  | P12 Full MVP release | N | Testing | all | Full regression on both apps + admin (3/3) | Regression list passes |  |  | 1 | Not started |  | Not requested
936 |  |  |  | P12 Full MVP release | N | Testing | all | Load test matching + booking APIs (k6) | p95 within targets | Performance |  | 1 | Not started |  | Not requested
937 |  |  |  | P12 Full MVP release | N | Security | all | Privacy review: retention jobs, data export, delete account | security/03 checklist ticked | Privacy | security/03 | 1 | Not started |  | Not requested
938 |  |  |  | P12 Full MVP release | N | Review | sprint | Sprint review + catch-up: finish leftovers, plan next sprint | Leftovers done or moved | Planning | plan/ | 1 | Not started |  | Not requested
939 |  |  |  | P12 Full MVP release | N | Ops | all | Play Store listing, privacy policy, screenshots | Listing approved |  |  | 1 | Not started |  | Not requested
940 |  |  |  | P12 Full MVP release | N | Ops | all | Production release + monitor first week | Release live |  |  | 1 | Not started |  | Not requested
941 |  |  |  | P12 Full MVP release | N | Review | milestone | Milestone demo: All 22 LLDs live; production release on Play Store | Demo recorded; README updated | Demo | plan/ | 1 | Not started |  | Not requested

## Decisions & Risks
Decisions & Risks
No. | Type | Item | Decision / mitigation | Source | Status
1 | Decision | Backend | Java 21 + Spring Boot 3 modular monolith, PostgreSQL 17 + PostGIS, Flyway, Redis non-authoritative | adr/0001, 0003, 0004 | Decided
2 | Decision | Persistence | Spring Data JPA (Hibernate) for aggregates; plain SQL (JdbcClient) for PostGIS candidate query and reports | adr/0018, lld-007 | Proposed
3 | Decision | Mobile apps | React Native + Expo (TypeScript): apps/customer and apps/worker in one pnpm monorepo, sharing packages/ui and packages/api | You (this chat) | Decided
4 | Decision | Admin web | React + Vite + TypeScript, React Router, TanStack Query; reuses packages/api | You (this chat) | Decided
5 | Decision | App libraries | Expo Router, TanStack Query, react-hook-form + zod, i18next, expo-secure-store, react-native-maps, expo-notifications | This tracker | Proposed
6 | Decision | Order | Vertical slices: build the API for a phase, then its screens, then demo. Pilot (cash-only) first, online money later | plan/01, lld/README | Decided
7 | Decision | Ids / money | UUIDv7 ids from the app; money as integer paise | adr/0018, adr/0006 | Decided
8 | Risk | Duration | 941 one-hour days ≈ 2.6 years at 7 h/week. Mitigate: ship the pilot first (Pilot = Y), re-plan after pilot feedback, cut P10–P12 scope if needed | This tracker | Open
9 | Risk | Learning curve | Java/Spring + React Native together. Mitigate: learning tasks before each new stack; Claude review on every task | This tracker | Open
10 | Risk | ₹99 advance | Advance is below visit charges (₹150–400) so no-show recovery is capped at ₹99. Decide before P10 | design/01 review | Open
11 | Risk | Motivation gaps | Missed days pile up. Mitigate: catch-up day each sprint; never skip ahead; small daily commits | This tracker | Open
12 | Risk | Design doc gaps | Some screens need endpoints not in LLDs (change password/email, my reviews, admin request list, refund preview). Add to the LLD before building that screen | design/01 review | Open